## Sheet1
ACCOF Preparations and implementation Plan
Responsible
Number | Activity | Responsible | Due date | Status | Status Date | Remarks | lead | sup1 | sup2 | sup3 | Colour Codes for Status reporting
1 | Concept Note preparation | DG, MSG | 2022-04-21 | Done | 2022-04-22 |  | DG | MSG
2 | Programme formulation | DG, MSG | 2022-04-21 | Done | 2022-04-22 |  | DG | MSG |  |  | Green | On time
3 | Invitation Letters drafting | DG, MSG, SDG | 2022-04-21 | Done | 2022-04-22 |  | DG | MSG | SDG |  | Yellow | Ongoing on time
4 | RCC presentation Guide | MSG, PHKT & HKN | 2022-04-21 | Sent | 2022-04-21 | Sent to RCC focal points | MSG | PHKT | HKN |  | Orange | Ongoing on delayed
5 | One Registration Link for all future ACCOFs | MSG & DIT | 2022-04-21 | Done | 2022-04-22 | Sent to ACCOF-03 list | MSG | DIT |  |  | Red | Late
6 | Signing of invitation letter | DG, SDG | 2022-04-22 | Email only | 2022-04-22 |  | DG | SDG
7 | Sending of Invitation Letters | SDG, MSG, GN | 2022-04-22 |  | 2022-04-22 | Email to be sent 25/04/2022 | SDG | MSG | GN
8 | Advertising of ACCOF on social media | SB & DIT | 2022-04-22 |  | 2022-04-22 |  | SB | DIT
9 | Virtual Banner design & development | SB, MSG, OC | 2022-04-25 |  |  |  | SB | MSG
10 | Create Zoom Link | GN | 2022-04-25 | created |  | https://us02web.zoom.us/j/84740377811?pwd=eGVPSGw0b2Z4SEo5TUlZK3NPTURoQT09 | GN
11 | Checking and downloading registrtion list | DIT & MSG | 26 - 28 April 2022 |  |  |  | DIT | MSG
12 | Sending of virtual banner to invited Guests | SB & SDG | 2022-04-26 |  |  |  | SB | SDG
13 | Continental presentation production | PHKT, HKN, MSG & IDD | 2022-04-26 |  |  |  | PHKT | HKN | MSG | IDD
14 | Clearance of final banner | DG | 2022-04-26 |  |  |  | DG
15 | Testing of zoom link & presentation lag | GN, DIT & KAL | 2022-04-27 |  |  |  | GN | DIT | KAL
16 | Sending of Zoom link to registered participants | SDG, MSG & GN | 2022-04-28 |  |  |  | SDG | GN | MSG
17 | Collection of RCC presentations | GN & HKN | 28-29/04/2022 |  |  |  | GN | HKN
18 | Uploading of RCC presentations to Google Drive and Thredds | MSG & DIT | 2022-04-29 |  |  |  | MSG | DIT
19 | Open the zoom link 30 minutes before | GN & DIT | 2022-04-29 |  |  |  | GN | DIT
20 | Moderate the eevnt | DG and SB | 2022-04-29 |  |  |  | DG | SB
21 | Monitor presentations during event | GN & AA | 2022-04-29 |  |  |  | GN | AA
22 | Draft report of the forum with summary of presentation, discussions and actions or recommendations , list of participants, programme and announcement in annexx | KAL, GN | 2022-05-03 |  |  |  | KAL | GN
23 | Review and revise the draft report | DG. MSG | 2022-05-06 |  |  |  | DG | MSG
24 | Final report and dissemination on THREDDS server and website | KAL, SB and AA | 2022-05-09 |  |  |  | KAL | SB | AA
25 | Clearance of final proceedings report | DG | 2022-05-09 |  |  |  | DG
26 | ACCOF Digital Flyer | SB, MSG, OC | 2022-05-20 |  |  |  | SB | MSG | OC
27 | Clearance of final Digital Flyer | DG | 2022-05-25 |  |  |  | DG
28 | Distribution of Digital Flyer | SB & OC | 2022-05-26 |  |  |  | SB
Code | Description
DG | Director General
SDG | Secretary to DG
MSG | Sunshine Mduduzi Gamedze
PHKT | Pierre Honore Kamsu Tamo
GN | Godefroid Nshirimana
HKN | Hubert Kabengela Nyamabu
SB | Serge Bayala
IDD | Ibrahim Dan Dije
KAL | Kamoru Abiodun Lawal
AA | Ali Abani
OO | Other Officer
ALL | Oranizing Committee (All)
DIT | Département Informatique et Télécommunications

## Sheet2
Zoom Meeting Link:
https://us02web.zoom.us/j/84740377811?pwd=eGVPSGw0b2Z4SEo5TUlZK3NPTURoQT09
Meeting ID: 847 4037 7811
Passcode: acmad2022