## Sheet1
ACCOF Preparations Plan
Colour Codes for Status reporting
Number | Activity | Responsible | Due date | Status | Status Date | Remarks
1 | Concept Note preparation | DG, MSG, GN | 21/04/2022 |  |  |  | Green | On time
2 | Programme formulation | DG, MSG, OC | 21/04/2022 |  |  |  | Yellow | Ongoing on time
3 | Invitation Letters drafting | DG, MSG, GN | 21/04/2022 |  |  |  | Red | Late
4 | Signing of invitation letter | DG, SDG | 22/04/2022
5 | Sending of Invitation Letters | SDG, MSG | 22/04/2022
6 | Virtual Banner design & development | SB, MSG, OC | 25/04/2022
7 | Sending of virtual banner to invited Guests | SB & SDG | 26/04/2022
8 | Advertising of ACCOF on social media | SB & IT | 22/04/2022
9 | ACCOF Digital Flyer | SB, MSG, OC | 13/05/2022
10 | RCC presentation Guide | MSG, PHKT & HKN | 21/04/2022 | Sent | 21/04/2022
11 | One Registration Link for all future ACCOFs | MSG & OC | 21/04/2022
12 | Checking and downloading registrtion list | IT & MSG | 26 -28/04/2022
13 | Zoom Link | GN | 25/04/2022
14 | Sending of Zoom link to registered participants | MSG & GN | 28/04/2022
15 | Testing of zoom link & presentation lag | GN, IT & OC | 26/04/2022
16 | Collection of RCC presentations | GN & HKN | 28/04/2022
17 | Continental presentation production | PHKT, HKN, MSG & IDD | 26/04/2022
Code | Description
DG | Director General
SDG | Secretary to DG
MSG | Sunshine Gamedze
PHKT | Pierre Honore Kamsu Tamo
GN | Godefroid Nshirimana
HKN | Hubert Kabengela Nyamabu
SB | Serge Bayala
IDD | Ibrahim Dan Dije
OO | Other Officer
OC | Oranizing Committee (All)