Summary of progress so far for Q2 2022 and plans for Q3 2022

Date: June 17 2022

- Objectives/activities and related projects

The primary objective is to develop ………. dataset and provide capacity building to NMHSs to on weather climate watch ….  The Q2 2022 work plan for my position detailing the key activities and deliverables are given in Appendix 1.

- Achievements to date

The main achievements so far are as follows:

- Evaluation of various satellite products over Africa. This manuscript, led by Mandela Houngnibo (agrometeorologist previously at AGRHYMET, now at Meteo Benin) is largely complete and is expected to be submitted during 2022.

- Finalisation of the TAMSAT satellite-gauge merging methodology. The method and software now exists to combine daily rain gauge measurements with TAMSAT daily rainfall estimates to create improved estimates of rainfall amount and calibrated uncertainty.

- Creation of a beta merged rainfall dataset for West Africa and early draft of accompanying manuscript. We have a created a complete 1983-2018 satellite-gauge merged rainfall product for West Africa at the daily and pentadal time-step and have an early draft of the paper which will describe the methodology and validation results.

- Extensive capacity building on satellite rainfall estimation, validation and the new merging methodology. To date, we have held two pan-Africa training events (July 2020, November 2021) and one training event focussed on the CREWS countries (July 2021). These events have provided a range of materials to enable NMHS to access, process and interrogate TAMSAT and other satellite rainfall products.

- Implementation of TAMSAT data within AGRHYMET agrometeorological monitoring bulletins. Starting in 2021, AGRHYMET now use TAMSAT v3.1 rainfall estimates for their agrometeorological monitoring bulletins. We are now working with them to create additional products (e.g. bespoke seasonal files) in preparation for the 2022 rainy season.

- Plans for the Q3 2022  ( outputs, activities, deliverables or milestones, timeline

- Xxxxxxxxxxxxxxxxxxxxxxxxxxxx

- Xxxxxxxxxxxxx

Appendix 1

Work Plan for Q2 2022

| Number-Outputs | Activities | Deliverables | Timeline in 2022 |
| --- | --- | --- | --- |
| 5.3.1 - Enhanced understanding of existing daily precipitation products available in West Africa | 5.3.1.1 - Evaluate TAMSAT and other satellite products for all West Africa using publicly available gauge gridded datasets | 5.3.1.1 - Gridded gap-filled TAMSAT rainfall estimates (v3.1) from 1983-delayed present, for West Africa and for Burkina Faso, Mali and Niger | June 20-July 15 |
|  | 5.3.1.2 - Evaluate TAMSAT and other satellite products for Burkina Faso, Mali and Niger using in-situ gauge records | 5.3.1.2 - Report providing a quantitative evaluation and discussion of each satellite product for all West Africa and for Burkina Faso, Mali and Niger, against gridded gauge datasets and other satellite datasets |  |
| 5.3.2 - Improved availability of daily precipitation products in West Africa | 5.3.2.1 - Development of a merging software | 5.3.2.1 - Satellite rainfall-gauge merging software and Africa-wide calibration maps |  |
|  | 5.3.2.2 - Generate satellite-gauge merged product for Burkina Faso, Mali and Niger | 5.3.2.2 - Archive of daily TAMSAT-gauge merged rainfall estimates from 1983-2018 for Burkina Faso, Mali and Niger, along with calibrated uncertainty estimates |  |
|  | 5.3.2.3 - Validation of satellite-gauge merged product for Burkina Faso, Mali and Niger | 5.3.2.3 - Quantitative assessment and discussion of the TAMSAT satellite-gauge merging methodology for the CREWS countries |  |
| 5.3.3 - Enhanced use of daily precipitation products by AGRHYMET and NMHSs | 5.3.3.1 - Exchanges by video-conference | 5.3.3.1 - Meeting reports |  |
|  | 5.3.3.2 - 5 to 8 days workshop in Reading | 5.3.3.2 - Workshop reports |  |