## Sheet1
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
WP0 Management & coordination
Project management
Partner meetings | bar: M1; M5; M9; M13; M17; M21; M25; M29; M33
Progress reports (D0.1) | bar: M13; M25; M36
Steering group meeting (D0.2) | bar: M2; M13; M25; M35
Strategic guidance
WP1 Development Climate Information Platform
Select 20 additional countries | bar: M1 to M2
Acquire contact information from 20 selected countries | bar: M1 to M2
Perform user requirement analyses (URA) | bar: M1 to M4
Expand platform to 3 countries for adaptation cases with existing indicators | bar: M1 to M5
Expand platform to 23 countries with existing indicators (D1.1) | bar: M1 to M10
Expand platform with additional indicators (max 10) based on URA (D1.1) | bar: M3 to M12
Explore possibility and relevance seasonal forecasts | bar: M2 to M14
Basic validation platform indicators | bar: M13 to M19
Expand platform with indicators calculated dynamically based on user input | bar: M15 to M26
Explore possibilities to expand platform with seasonal forecasts (D1.1) | bar: M26 to M35
Train stakeholders in 23 countries (D1.2) | bar: M14 to M34
WP2 Development strategic adaptation plans
Write policy document ~ (strategic) adaptation plans for African agricultural sector (D2.1)
1) Analyse (climate and non-climate related) strengths and weaknesses of agricultural sector in (3) selected countries (literature) | bar: M5 to M8
2) Analyse evolution of selected agro-climate indicators in the selected countries for different time horizons (e.g. 2030-2050-2075) based on output of climate information platform. | bar: M8 to M14
3) Assess threats and opportunities for agriculture given climate change prognosis (literature + stakeholder survey) for different time horizons. | bar: M15 to M18
4) Describe sets of generic adaptation options (including transformation) for different levels of climate change and different farming systems, and develop decision trees and adaptation pathways | bar: M18 to M24
5) Test usefulness of decision trees and adaptation pathways in selecting adaptation options and priorities for pilot adaptation cases | bar: M23 to M27
6) Feedback workshop with stakeholders | bar: M28
7) Develop guidelines for medium and long term strategic adaptation planning based on climate information platform data (including institutional, organisational etc. aspects). | bar: M29 to M30
8) Develop template and guidelines for strategic adaptation plans based on insights obtained during the previous steps | bar: M30 to M32
9) Stakeholder feedback (workshops and/or surveys) | bar: M32 to M33
10) Finalise template and guidelines for strategic adaptation plans | bar: M33 to M36
Write report on insights for access to international (adaptation) climate finance for African countries (D2.2
1) Delineate research design and identify contacts at participating countries | bar: M1 to M3
2.1) Conduct literature review via desk research | bar: M4 to M8
2.2) Conduct qualitative survey among participating countries | bar: M9 to M10
2.3) Conduct remote interviews with stakeholders and subject matter experts | bar: M11 to M14
2.4) Consolidate and synthesize findings from research | bar: M15 to M16
3.1) Draft first version of final report | bar: M17 to M19
3.2) Draft final version of final report | bar: M20
WP3 Development Pilot Adaptation Cases
Select adaptation use cases/entrepreneurs Senegal (M3.1) | bar: M5 to M8
Pre investment coaching Senegal | bar: M8 to M14
Setting up partnerships with Flemish companies (Senegal) | bar: M14 to M16
Post investment follow up & coaching (Senegal) | bar: M16 to M36
Select adaptation use cases/entrepreneurs Uganda & Malawi (M3.1) | bar: M9 to M12
Pre investment coaching Uganda & Malawi | bar: M12 to M18
Setting up partnerships with Flemish companies (Uganda & Malawi) | bar: M18 to M20
Post investment follow up & coaching (Uganda & Malawi) | bar: M20 to M36
3x2 field visits adaptation use cases + report (M3.2) | bar: M26; M30
Evaluate adaptation use cases (D3.1) | bar: M31 to M34
WP4 Dissemination
Dissemination of Climate Information Platform | bar: M13 to M36
Dissemination of strategic adaptation plans
Video’s use cases | bar: M25 to M36
Dissemination of use cases (D3.2) | bar: M31 to M36