## Effort, costs
# | Name | Monthly rate | Funding rate | Effort (PM) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Total | Share | Personnel Cost (€) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Partner cost | Requested | Share
1 | WMO | 0 | 100% | WMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | WMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2 | BSC | 4500 | 100% | BSC | 28 | 10 | 0 | 26 | 58 | 18 | 0 | 2 | 142 | 100% | BSC | 126000 | 45000 | 0 | 117000 | 261000 | 81000 | 0 | 9000 | 639000 | 639000 | 100%
3 | MettOffice | 0 | 100% | MettOffice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | MettOffice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4 | WEMC | 0 | 100% | WEMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | WEMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5 | SADC CSC | 0 | 100% | SADC CSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | SADC CSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6 | EDF | 0 | 100% | EDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | EDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7 | ACMAD | 5366.84 | 100% | ACMAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | ACMAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
8 | CSIR | 0 | 100% | CSIR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | CSIR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
9 | LGI | 6500 | 100% | LGI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | LGI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
10 | WITS University | 0 | 100% | WITS University | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | WITS University | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
11 | UCT | 0 | 100% | UCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
12 | Amigo Climate | 5230 | 100% | Amigo Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Amigo Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
13 | MMS | 0 | 100% | MMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | MMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
14 | TMA | 0 | 100% | TMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | TMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
15 | JRC-Ispra | 0 | 100% | JRC-Ispra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | JRC-Ispra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
16 | SSA | 0 | 100% | SSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | SSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
17 | Plan Italia | 0 | 100% | Plan Italia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Plan Italia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
18 | COWI | 0 | 100% | COWI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | COWI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
19 | DCCMS | 0 | 100% | DCCMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | DCCMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
20 | Landbank | 0 | 100% | Landbank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Landbank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Total effort | 28 | 10 | 0 | 26 | 58 | 18 | 0 | 2 | 142 |  | Total cost | 126000 | 45000 | 0 | 117000 | 261000 | 81000 | 0 | 9000 | 639000 | 639000 | 72.61%
|  |  |  | WP share | 19.72% | 7.042% | 0% | 18.31% | 40.85% | 12.68% | 0% | 1.408% |  |  | WP share | 19.72% | 7.042% | 0% | 18.31% | 40.85% | 12.68% | 0% | 1.408%
48 months
| TOTAL Figures to include |  |  | Subcontracting (€) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Total | Requested | Other direct costs (€) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Partner ODC | Requested | ODC share
| MettOffice | 50PM | 470000 | WMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMO | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| WEMC |  | 400000 | BSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BSC | [7 empty] | 65000 | 65000 | 65000 | 10.17% | travel, equipment, publication audit cost
| SADC |  | 300000 | MettOffice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MettOffice | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| JRC | 40PM | 500000 | WEMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WEMC | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| COWI | 24PM | 150000 | SADC CSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SADC CSC | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| SSA | 60PM | 500000 | EDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EDF | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| WITS |  | 53000 | ACMAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ACMAD | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| ACMAD | 134,4PM | 614167.19 | CSIR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CSIR | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| BSC | 142PM | 880000 | LGI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LGI | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| LGI | 68PM |  | WITS University | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WITS University | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
| AMIGO Climate | 66PM |  | UCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UCT | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | Amigo Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Amigo Climate |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | #DIV/0! | travel, equipment, publication audit cost cloud system
|  |  |  | MMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MMS | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | TMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TMA | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | JRC-Ispra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JRC-Ispra | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | SSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SSA | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | Plan Italia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan Italia | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | COWI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | COWI | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | DCCMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DCCMS | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | Landbank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Landbank | [8 empty] | 0 | 0 | #DIV/0! | #DIV/0!
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total ODC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 65000 | 7.386%
|  |  |  | WP share | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | WP share | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  |  |  | INDIRECT (€) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Total | Requested | TOTAL DIRECT (€) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Total | Requested | Share
|  |  |  | WMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | BSC | 31500 | 11250 | 0 | 29250 | 65250 | 20250 | 0 | 18500 | 176000 | 176000 | BSC | 126000 | 45000 | 0 | 117000 | 261000 | 81000 | 0 | 74000 | 704000 | 704000 | 100% | CFS
|  |  |  | MettOffice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MettOffice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | WEMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WEMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | SADC CSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SADC CSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | EDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | ACMAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ACMAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | CSIR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CSIR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | LGI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LGI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | WITS University | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WITS University | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | UCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Amigo Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Amigo Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | MMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | TMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | JRC-Ispra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JRC-Ispra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | SSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Plan Italia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan Italia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | COWI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | COWI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | DCCMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DCCMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Landbank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Landbank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Total | 31500 | 11250 | 0 | 29250 | 65250 | 20250 | 0 | 18500 | 176000 | 176000 | Total | 126000 | 45000 | 0 | 117000 | 261000 | 81000 | 0 | 74000 | 704000 | 704000
|  |  |  | Share | 17.9% | 6.392% | 0% | 16.62% | 37.07% | 11.51% | 0% | 10.51% |  |  | WP share | 17.9% | 6.392% | 0% | 16.62% | 37.07% | 11.51% | 0% | 10.51%
[15 empty] | TOTAL COSTS (€) | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Total | Requested | Share
[15 empty] | WMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | BSC | 157500 | 56250 | 0 | 146250 | 326250 | 101250 | 0 | 92500 | 880000 | 880000 | 100%
[15 empty] | MettOffice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | WEMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | SADC CSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | EDF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | ACMAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | CSIR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | LGI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | WITS University | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | UCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | Amigo Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | MMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | TMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | JRC-Ispra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | SSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | Plan Italia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | COWI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | DCCMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | Landbank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[15 empty] | Total | 157500 | 56250 | 0 | 146250 | 326250 | 101250 | 0 | 92500 | 880000 | 880000
[15 empty] | WP share | 17.9% | 6.392% | 0% | 16.62% | 37.07% | 11.51% | 0% | 10.51%

## Log
DATE | WP | CHANGES

## Efforts by task
To ADAPT
Partner | 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | WP1 | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | WP2 | 3.1 | 3.2 | 3.3 | 3.4 | 3.5 | 3.6 | WP3 | 4.1 | 4.2 | 4.3 | 4.4 | WP4 | 5.1 | 5.2 | 5.3 | 5.4 | WP5 | 6.1 | 6.2 | 6.3 | 6.4 | WP6 | 7.1 | 7.2 | 7.3 | 7.4 | WP7 | 8.1 | 8.2 | 8.3 | WP8
WMO | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
BSC | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
MettOffice | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
WEMC | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
SADC CSC | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
EDF | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
ACMAD | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
CSIR | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
LGI | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
WITS University | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
UCT | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Amigo Climate | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
MMS | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
TMA | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
JRC-Ispra | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
SSA | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Plan Italia | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
COWI | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
DCCMS | [23 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Landbank | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary
# | Short name | Country | (A) Direct personnel costs | (B) Other direct costs | (C) Direct costs of subcontracting | (D) Direct costs of providing financial support to third parties | (E) Costs of inkind contributions not used on the beneficiary's premises | (F) Indirect Costs /€ (0.25(A+B-E)) | (G) Special unit costs covering direct & indirect costs | (H) Total estimated eligible costs (A+B+C+D+F+G) | (I) Reimbursement rate (%) | (J) Max.EU Contribution (H*I) | (K) Requested EU Contribution/
1 | WMO | CH | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
2 | BSC | ES | 639000 | 65000 | 0 |  | 0 | 176000 |  | 880000 | 100% | 880000 | 880000
3 | MettOffice | UK | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
4 | WEMC | UK | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
5 | SADC CSC | BW | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
6 | EDF | FR | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
7 | ACMAD | NE | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
8 | CSIR | ZA | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
9 | LGI | FR | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
10 | WITS University | ZA | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
11 | UCT | ZA | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
12 | Amigo Climate | IT | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
13 | MMS | MU | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
14 | TMA | TZ | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
15 | JRC-Ispra | BE | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
16 | SSA | IT | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
17 | Plan Italia | IT | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
18 | COWI | DK | 0 | 0 |  |  |  | 0 |  | 0 | 100% | 0 | 0
19 | Amigo Climate | MW | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
20 | Landbank | ZA | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 100% | 0 | 0
TOTAL |  |  | 639000 | 65000 | 0 | 0 | 0 | 176000 | 0 | 880000 |  | 880000 | 880000

## Deliverables
Deliverable | Title | Lead by | Type | Dissemination level | Due | Due Date | Type code | Meaning
D1.1 | Assessment report for generation quantity and quality of slags and MSWI bottom ashes in Europe | TU Delft | R | PU | M8 |  | R | Document, report
D1.2 | Assessment report on recycling technologies for non-ferrous slags and MSWI bottom ash | MEFOS | R | PU | M8 |  | DEM | Demonstrator, pilot, prototype
D1.3 | Report on trends and forecast of recycling technologies and the related environmental regulations | Coolrec | R | PU | M18 |  | DEC | Websites, patent filings, videos
D2.1 | Chemical and mineralogical characterization report on feeds | ER | R | PU | M9 |  | OTHER
D2.2 | Technical report on comminution tests | BRGM | R | PU | M12 |  | ETHICS | Ethics requirement
D2.3 | Technical report on concentration tests | ULIEGE | R | PU | M24 |  | ORDP | Open Research Data Pilot
D2.4 | Geometallurgical modelling report | ER | R | PU | M46
D3.1 | Selected demonstration cases. Guidelines for Task 3.2-3.6. | MEFOS | R | PU | M12 |  | Dissemination level | Meaning
D3.2 | Slag modification report | MEFOS | R | PU | M18 |  | PU | Public
D3.3 | Report on removal of impurities by roasting | TU Delft | R | PU | M18 |  | CO | Confidential, only for members of the consortium (including the Commission Services)
D3.4 | Innovative oxy-carbochlorination concept report | BRGM | R | PU | M18 |  | EU-RES | Classified Information: RESTREINT UE (Commission Decision 2005/444/EC)
D3.5 | Metal extraction efficiency report | FEhS | R | PU | M20 |  | EU-CON | Classified Information: CONFIDENTIEL UE (Commission Decision 2005/444/EC)
D3.6 | Pyrometallurgy pilot report | MEFOS | R | CO | M24 |  | EU-SEC | Classified Information: SECRET UE (Commission Decision 2005/444/EC)
D4.1 | Results of direct leaching performances of non-ferrous slags and bottom ashes | TU Delft | R | PU | M18
D4.2 | Assessment of leaching performances on residues from pyrometallurgy | Chalmers | R | PU | M36
D4.3 | Report on optimized hydrometallurgical processing technologies with characterization of the final products | CEA | R | PU | M36
D5.1 | Characterisation of solid precursor materials | MUL | R | PU | M36
D5.2 | Procedures for enhancing the valorisation potential of solid precursor materials | MUL | R | PU | M40
D5.3 | Valorisation of coarse materials | FEhS | R | PU | M42
D5.4 | Geopolymer mix design | MUL | R | PU | M42
D5.5 | Characterisation of geopolymer products | MUL | R | PU | M46
D6.1 | Preliminary environmental life cycle screening of advanced metal recovery processes | 2-0 LCA | R | PU | M30
D6.2 | Sustainability assessment of advanced metal recovery | 2-0 LCA | R | PU | M48
D6.3 | Preliminary market assessment and impact study on EU supply criticality | LGI | R | PU | M48
D7.1 | Communication and dissemination plan | LGI | R | PU | M3
D7.2 | AROMES project website | LGI | DEM | PU | M4
D7.3 | Final report on communication and dissemination activities | LGI | R | PU | M48
D7.4 | Intermediate exploitation plan | LGI | R | PU | M24
D7.5 | Final exploitation plan | LGI | R | PU | M48
D8.1 | Online workspace | LGI | R | CO | M1
D8.2 | Project Quality Plan | LGI | R | CO | M2
D8.3 | Data Management Plan | LGI | R | PU | M4
D8.4 | Intermediate Advisory Board recommendations | BRGM | R | PU | M24
D8.5 | Final Advisory Board recommendations | BRGM | R | PU | M48

## Milestones
Milestone | Title | WP(s) | Lead by | Due | Due Date | Output

## GANTT
Leader | Tasks/timing | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48
| WP1 - Baseline: strategies, trends, assessments and forecasts of slags and bottom ashes production/production technologies state | M6: MS1
Task 1.1 Assessment of current status of slag and bottom ash generation | bar: M1 to M6
Task 1.2 Inventory of current recycling methods and their effectiveness and capacities | bar: M1 to M6
Task 1.3 Inventory of the slag and ash qualities and limitations | bar: M3 to M6
| Task 1.4 Regulatory assessment and requirements for slag and ash use and disposal | M8: D1.1 D1.2
| Task 1.5 Integration, assessment and formulation of detailed research objectives | M18: D1.3
| WP2 - Sampling, preparation, screening and characterization Selective smart size reduction, physical concentration | M12: MS2; M24: MS3 MS4
Task 2.1 Produce twin samples for each feed | bar: M1 to M3
| Task 2.2 Detailed mineralogical and chemical characterization of the targeted material | M9: D2.1
| Task 2.3 Mechanical preparation (smart size reduction) | M12: D2.2
| Task 2.4 Beneficiation and concentration | M24: D2.3
| Task 2.5 Geometallurgical modelling | M46: D2.4
| WP3 - Innovative pyro-metallurgical process | M20: MS5
| Task 3.1 Thermodynamic modelling for selection of demonstration cases and processing approaches | M12: D3.1
| Task 3.2 Slag modification | M18: D3.2
| Task 3.3 Roasting and calcination of the chosen test materials | M18: D3.3
| Task 3.4 Selective recovery of metals by innovative oxy-carbo-chlorination | M18: D3.4
| Task 3.5 Final metal extraction | M20: D3.5
| Task 3.6 Mini pilot demonstration | M24: D3.6
| WP4 - Innovative hydro-metallurgical process | M30: MS6; M36: MS7
| Task 4.1 Direct leaching on genuine materials | M18: D4.1
Task 4.2 Leaching of products resulting from conventional thermal treatments | bar: M12 to M30
Task 4.3 Leaching of products resulting from carbochlorination | bar: M18 to M30
| Task 4.4 Metal extraction process from leachates | M36: D4.2 D4.3
WP5 - Geo-polymerisation
Task 5.1 Characterisation of solid precursor materials | bar: M3 to M24
| Task 5.2 Pre-treatment of solid precursor materials | M36: D5.1
| Task 5.3 Valorisation of coarse materials and geopolymer mix design | M40: D5.2; M42: D5.3
| Task 5.4 Characterisation of geopolymer products | M42: D5.4; M46: D5.5
| WP6 - Environmental, economic and social Life Cycle Assessment | M38: MS8; M42: MS9; M46: MS10
| Task 6.1. Preliminary environmental screening | M30: D6.1
Task 6.2 Laboratory pilot testing | bar: M30 to M42
| Task 6.3 Sustainability assessment of advanced metal recovery | M48: D6.2
| Task 6.4 Preliminary market assessment and impact study on EU supply criticality | M48: D6.3
| WP7 - Communication, dissemination and exploitation | M18: MS11; M42: MS12
| Task 7.1 Communication and general public awareness | M3: D7.1; M4: D7.2; M48: D7.3
Task 7.2 Scientific dissemination
Task 7.3 Clustering with other projects
| Task 7.4 Exploitation plan | M24: D7.4; M48: D7.5
WP8 - Management
| Task 8.1 Project coordination | M1: D8.1; M2: D8.2; M4: D8.3; M6: PM; M12: PM; M18: PM; M24: PM; M30: PM; M36: PM; M42: PM; M48: PM
Task 8.2 Contractual and financial management
| Task 8.3 Advisory Board | M24: D8.4; M48: D8.5
|  |  | Project meeting |  |  |  | Deliverable |  |  | Milestone