Table 1: Regional component of the “Climate Services for Increased Resilience in the Sahel” project

| Activities | Total Budget |
| --- | --- |
| A.2 A.2.1 Review of ACMAD and countries’ datasets, processes, methods, tools, products and services: • generation of RCC products and provision of required services for climate resilience Deliverables include: - 2 technical notes to support long range forecasts discussions and climate outlook at national level with emphasis on pilot countries; - 2 bulletins with outlook information and advices for experts responsible for contingency planning and action in the DRR community - 2 briefs or synthesis climate information for climate resilience decision makers containing expected hazards, potential impacts and suggested measures to update contingency plans These deliverables were provided in May and June 2018 valid for June-September and July-October 2018 periods respectively The needs satisfied with the deliverables include:; products and services on onset, intensity, distribution and withdrawal of the monsoon rainfall; hazards and vigilance maps on the disruption in rainfall distribution; heavy rains frequencies and droughts information for regional organizations active in GFCS sectors like agriculture, water, health, DRR. Commitment details: 1 climate experts at $4000/month for half time in May and 20% of time in June 2018 generating products and drafting technical notes and bulletins Sub-total : $4000*(1/2 + 20/100) = $2800 •Commitment detail: 1 Team leader (part time) for 58% of time in May and 15% of time in June 2018 with expertise on climate services delivery, activities planning and budgeting, monitoring, supervision, review, partnership development and reporting (final narrative and technical report). Sub-total: (58/100+15/100)*$6000= $4400 | 7.2K |
| I. Accounting, administration and financial reporting support Deliverables include: - Statement of budget execution, journals, bank and accounts reconciliations, statements of expenditure and financial reports, project records Commitment detail: administration and finance support staff for the project at $3000*((1/2+ 27/100) =$2310 for half time in June and 27% July 2018. | 2.31K |
| - Miscellaneous/unforeseen expenses (postal services, exchange rate losses, bank and other charges) at $490 | 0.49K |
| TOTAL Budget | 10,000 USD |