## GanttChart
Web Mapping Technology
ACMAD
| Project Start Date | 2022-04-11 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40
| Project Lead | Romeo Sosthene Nkurunziza | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09
 | time axis 2022-04-11 to 2023-01-15
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2022-04-11 to 2023-01-15
| Web Mapping Technology | Romeo |  | 2022-04-12 | 2023-04-11 | 365 |  | 261 | bar: 2022-04-11
1 | Task 1: Install System Server At ACMAD |  |  | 2022-04-11 | 2022-04-25 | 15 | 0% | 11
D1.1 | Document with a description of computers, network structure and operating system software installed at ACMAD to be used in the project | A. Abani |  | 2022-04-11 | 2022-04-25 | 15 | 0% | 11
D1.2 | Reporting and detailed work plan for Task2 | Romeo Sosthene |  | 2022-04-22 | 2022-04-25 | 4 |  | 2
2 | Task2: Software Installation | M. Kambi/Abani |  | 2022-04-25 | 2022-05-10 | 16 |  | 12
D2.1 | installing Apache, | M. Kambi/Abani |  | 2022-04-25 | 2022-04-25 | 1 | 0% | 1
D2.2 | installing PHP | M. Kambi/Abani |  | 2022-04-26 | 2022-04-26 | 1 | 0% | 1
D2.3 | installing PostgreSQL/POSTGIS | M. Kambi/Abani |  | 2022-04-27 | 2022-04-27 | 1 | 0% | 1
D2.4 | installing POSTGIS | M. Kambi/Abani |  | 2022-04-28 | 2022-04-28 | 1 | 0% | 1
D2.5 | Installing Other appropriete Packages | M. Kambi/Abani |  | 2022-04-29 | 2022-04-29 | 1 | 0% | 1
D2.6 | database server in the DMZ | M. Kambi/Abani |  | 2022-05-02 | 2022-05-02 | 1 |  | 1
D2.7 | Report on the installation of the base software system at ACMAD | Romeo |  | 2022-05-03 | 2022-05-04 | 2 |  | 2
D2.8 | Performance test of the Database and its connections with the external platform and the internal platform | M. Kambi/Abani |  | 2022-05-05 | 2022-05-06 | 2 |  | 2
D2.9 | Detailed work plan for Task 3 | Romeo Sosthene |  | 2022-05-09 | 2022-05-10 | 2 |  | 2
3 | Task3: Adoption of the stylesheet of the CMS to work with ACMAD standards. | M. Kambi/A.Abani/Godefroid |  | 2022-05-13 | 2022-05-13 |  |  | 1
D3.1 | Creation of the initial menu, | M. Kambi/Abani |  | 2022-05-13 | 2022-05-16 | 4 | 0% | 2
D3.2 | Filling of the pages with ‘semi-static’ content | M. Kambi/Abani |  | 2022-05-17 | 2022-05-21 | 5 | 0% | 4
D3.3 | Upgraded stylesheet scripts necessary for the adaptation of the look and feel of the system | M. Kambi/Abani |  | 2022-05-22 | 2022-05-24 | 3 | 0% | 2
D3.4 | Proposed design of the menu and report on feedback of user community | Godefroid |  | 2022-05-25 | 2022-05-27 | 3 | 0% | 3
D3.5 | Agreed design of the menu and implementation in MUKAU, filling of static page content | Godfroid/Kambi |  | 2022-05-28 | 2022-05-30 | 3 | 0% | 1
D3.6 | Detailed work plan for Task 4. | Romeo Sosthene |  | 2022-05-25 | 2022-05-27 | 3 | 0%
4 | Task4: Coversion of base spatial data to the PostgresSQL and PostGIS | M. Kambi/Abani |  |  | - |  |  | -
D4.1 | Upgraded software scripts in PL/pgSQL to fill the databases with data provided by the JRC in PostgreSQL export format | M. Kambi/Abani |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
D4.2 | Filled databases and report on performance metrics |  |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
D4.3 | Detailed work plan for Task 5 | Romeo Sosthene |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
5 | Task 5: Integration of SPI computation module and module to synchronise soil moisture data with the JRC | Kambi/Leo |  |  | - |  |  | -
D5.1 | Document describing the successful installation of the two modules on both the internal as well as the external system | Romeo/Kambi |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
D5.2 | Integration of Web Map Service (WMS) layers displaying actual disaster risk in ACMAD’s main web portal | M. Kambi/Abani |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
D5.3 | Detailed work plan for Task 6 |  |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
6 | Task 6: Publication of the system on the Internet | M. Kambi/Abani |  |  | - |  |  | -
D6.1 | Publication of the system on the Internet |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
D6.2 | Report system implementation (as described in section 2) and working system. | Romeo Sosthene |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
D6.3 | Detailed work plan for Task 7 | Romeo Sosthene |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
7 | Task 7 Automation of components of data processing chain at ACMAD and integration of MUKAU in order to generate a 10-day bulletin focussed on Drought with standard maps and legends | Kambi/Pierre/Ibrahim |  |  | - |  |  | -
D7.1 | Publication of the system on the Internet | Kambi/Ali Abani/Serge |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
D7.2 | automate the processing of MODIS NDVI data, including the computation of anomalies. | Kambi/Pierre/Ibrahim |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
D7.3 | Development of software to store the following parameters of the bulletin in MUKAU PostgreSQL database: . | kambi/Leo |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
D7.4 | Total rainfall, rainfall anomaly, maximum temperature, Standard Precipitation Index for 1, 3 and 6 cumulative months. | Kambi/Pierre/Ibrahim |  | 2018-02-01 | 2018-02-01 | 1 | 0% | 1
Note on A9: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B9: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C9: Task Lead Enter the name of the Task Lead in this column.
Note on D9: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E9: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F9: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G9: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I9: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.