Annex: Matrix of the Programme of Action (Phase II: 2021-2025) to Implement the Sendai Framework for Disaster Risk Reduction 2015-2030

In line with the Africa Regional Strategy for Disaster Risk Reduction

| Priority 1: Understanding disaster risk PoA Target 1: Substantially increase the number of countries with DRR in their educational systems at all levels, as both stand-alone curriculum and integrated into different curricula |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic areas of intervention | Key activities | Level of Implementation | Lead Institution/ Organisation | Results | Targets? | PoA/SFDRR Targets to which they contribute (bring out PoA targets) | Timeframe |
| 1.1. Risk assessment and analysis | 1.1.1 Support MS on disaster risk assessment and analysis | National | MS, RECs AUC, UNDRR | a) MS have increased technical capacity to sustainably undertake disaster risk assessment and analysis. | 30 MS with technical disaster risk assessment and analysis capacity. | F-1 – F5 | Dec 2022 |
|  | 1.1.2 Mapping of risk assessment and analysis gaps/capacity building needs | Regional and national | RECs and MS, UN agencies and other international and regional organisations | a) Disaster risk assessment needs identified | 30 MS with needs identification. | F-1 – F5 | March 2022 |
|  | 1.1.3 Harmonisation of risk assessment and analysis approaches, tools and methodologies | Continental, regional | AUC, RECs RECs, MS, UN agencies, regional and international organisations | a) Guidelines for disaster risk assessment developed and disseminated b) MS are undertaking disaster risk assessment using the harmonised tools and methodologies | 30 MS with guidelines. 30 MS undertaking disaster risk assessments. | F-1 – F5 | June 2022 |
|  | 1.1.4 Develop and update disaster risk profiles | National | MS RECs, AU agencies, UN agencies and other international and national organisations | a) MS have comprehensive/ multi-hazards and agile disaster risk profiles. | 30 MS with updated disaster risk profiles. | F-1 – F5 | Dec 2022 |
|  | 1.1.5) Consolidate/adapt guidelines for local climate and disaster risk assessments and their use in local development planning, ensuring the complementarities of proven traditional, indigenous and local knowledge and practices, and science and technology. | National | MS, National scientific and research organisations and other national organisations | - Broad guidelines for the use of indigenous knowledge (systems) in climate and disaster risk assessments and local development planning. - Indigenous Knowledge and Systems for climate and disaster risk identification, monitoring and assessment are documented and recorded in knowledge and information sharing platform (see 1.3) | 30 MS with local disaster risk assessments. | E-2 |  |
|  | 1.1.6) Document, systematise and promote use of indigenous knowledge on climate and disaster risk identification, monitoring and assessment at the local level. | National | MS, National scientific and research organisations and other national organisations | - Evidence of Indigenous Knowledge Systems used in national level reporting. | 25 MS with Indigenous Knowledge Systems incorporated into national level planning. | E-2 |  |
|  | 1.1.7) Programming to support priority RECs and MS on climate and disaster risk assessment and analysis. | Continental | AUC, UN agencies and other international and regional organisations | - Programmes and projects linked to funding in support of systems-level climate and disaster risk assessment and analysis for priority RECs and MS, focussing on risk assessments. - Risk assessments to feed into monitoring and evaluation. - Mainstreaming of risk assessments report into National development plans | All programming supports priority RECs and MS. 30 MS with evidence of risk assessments in M&E. 30 MS with risk assessments informing National development plans. | E-2 | Dec 2022 June 2023 July 2024 |
| 1.2. Research and innovation in DRR | 1.2.1 Build partnership with academic and research institutions to strengthen science-policy interface | Continental, regional and national | AUC, RECs and MS, academic and research networks, UN organisations and other international, regional and national organisations. | a) Dialogue among scientists and policy makers on DRR is increased. b) Research undertaken by African scientists are applied for policy making and implementations. | Biennial conferences and workshops between academia and policy makers. | F-1 – F5 | October 2022 |
|  | 1.2.2 Support African scientists to undertake tailored disaster risk research and innovation | Continental, regional and national | AUC, RECs and MS academic and research networks, RECs, UN organisations and other international, regional and national organisations. | a) Supported scientist developed innovative solutions for DRR b) African scientists generate research findings with continental impacts and global implications | 10 research interventions per REC 10 academic articles per REC per year | F-1 – F5 | Dec 2022 Dec 2022 |
|  | 1.2.3 Promote disaster risk education | Continental | AUC /AfSTAG academic and research networks, UN organisations and other international, regional and national organisations. | a) Increased integration of DRR in Curricula b) Increased number of African universities with DRR as stand-alone speciality or modules | 30 MS with DRR in curricula. 3 universities per REC with stand-alone DRR specialty modules. | F-1 – F5 PoA Target 1 | Dec 2023 Dec 2023 |
|  | 1.2.4) Provide research, technical and scientific advice to RECs and MS for climate and disaster risk assessment and analysis, including to analyse systemic risk. | Continental | AUC/ Af-STAG, academic and research networks, UN agencies and other International and regional organisations | - Allocation of a working budget and support to the Af-STAG and AYAB. - Climate and disaster risk assessment and analysis as a standing agenda item on the Af-STAG. - (Peer) review of climate and disaster risk assessment and analysis methodologies, tools and results. - Public-private partnerships for the application of science, technology and innovation in climate and disaster risk assessment and analysis. - Research library/publications etc | Annual budget approved. Evidence in each minutes of the Af-STAG 30 Peer reviews One PPP per REC One online research library (see 1.4) linked to a university per REC and 10 academic articles per REC per year (see 1.2.2) | F-6 | Dec 2022 Dec 2022 Annually Dec 2025 Dec 2023 Dec 2023 |
| 1.3 Disaster loss and damage data systems. | 1.3.1) Support Member states to use DesInventar, Sendai Framework Monitor (including the 5 additional targets of the PoA). | Continental | UNDRR, AUC, RECs | - Continued reporting of disaster loss data on the DesInventar Sendai system. - Accurate inclusion of disaster loss data in the biennial report on the implementation of the SFDRR and PoA. - Workshops and seminars | Reporting by all MS by July 2022. | A-D | Continuous Biennially |
|  | 1.3.2) Validating records on the DesInventar Sendai system, Sendai Framework Monitor and EM-DAT database. | National | RECs, MS | - Validation workshops of disaster loss data on the DesInventar Sendai system, Sendai Framework Monitor and EM-DAT database in line with biennial reporting (see 1.8). | One biennial validation workshop in each REC. | A-D | Biennially |
| 1.4 Interactive knowledge and information sharing. | 1.4.1) Develop and enhance information management skills and capacities. | Regional | AUC, UNDRR, RECs, MS, AYAB | - Capacity and training interventions and enhance information and data management skills and capacities at national, REC and AU level. - Platform for data and information sharing | At least one annual capacity and training interventions per REC for enhance information and data management. | F6 – F8 | Annually |
|  | 1.4.2) Generate and disseminate risk knowledge and risk information for decision making, including for cross-border, cross-cultural, gender, disability and age issues. | Regional and National | RECs, MS, AYAB, academic/research institutions; UN agencies, International, regional and national organisations. | - Gender, disability and age disaggregated data are generated and disseminated for risk assessment and development. | All MS to have Gender, disability and age disaggregated data generated and disseminated | G-5 | Dec 2023 |
|  | 1.4.3) Risk information management systems enhance the receptivity and compliance with risk information by ensuring that messages are understandable, consistent and targeted at known recipient stakeholders. | Regional and national | MS, RECs, Private sector, academic institutions and regional knowledge centres/networks | - Regional Disaster Risk Management Information and Communication Systems (DRMICS) have been developed and is publicly available online. - Risk information is used to inform development planning at all levels. | All RECs have developed and activated DRMICS. | F-5 | Dec 2024 |
| 1.5 Science-driven disaster risk reduction | 1.5.1) Establish regional Science and Technology Advisory Groups (REC-STAGs). | Regional | RECs, MS, Af-STAG | - REC-STAGS are established and functional/operational. | One REC-STAG per REC. | F-5 | Oct 2023 |
|  | 1.5.2) Rehabilitate, modernise and expand basic hazard monitoring and data infrastructure in line with existing regional and national systems. | Regional and national | MS, RECs AUC/Af-STAG; UN agencies, International, regional and national organisations | - Basic regional and national hazard monitoring and data infrastructure is operational. - Reporting on current and future disaster risks and the status of DRM efforts. | 30 MS | G-5 | June 2023 |
|  | 1.5.3) Maintain and strengthen scientific institutions and networks. | Continental and Regional | AUC/Af-STAG; RECs UN agencies and International and regional organisations | - Guidance on terminology, data, methodologies and standards for hazard and risk assessments and modelling. - Communicate complex scientific information and evidence to support the decision-making of DRR policymakers and other stakeholders. - Monitor progress towards internationally agreed targets for reducing disaster losses in the PoA. - Develop strategic scientific DRR for Resilience research agenda for RECs and the AU. | All RECs | G-5 PoA Additional Target 5 | Dec 2022 Continuous Continuous Nov 2022 |
| 1.6) Inventory and mainstreaming of disaster risk reduction, resilience and climate risk in educational systems. | 1.6.1) Conduct MS level assessments of the presence of disaster risk reduction, resilience and climate risk in qualifications, professional courses and integrated into modules/subjects at all levels. | Regional and national | RECs MS, AUC, UN agencies and International and regional organisations | - 50% of all MS have an up-to-date database of disaster risk reduction, resilience and climate risk in qualifications, professional courses, and integrated modules/subjects at all levels by 2022. - 100% of all MS has an up-to-date database of disaster risk reduction, resilience and climate risk in qualifications, professional courses and integrated modules/subjects at all levels by 2023. | 28 MS 55 MS | G2 – G4 | Dec 2022 Dec 2023 |
|  | 1.6.2) Identify low resourced MS and conduct needs analysis of assistance with DRR integration and mainstreaming into educational systems at all levels. | Regional | RECs, MS, AF-STAG, academic institutions. | - Priority countries per REC has been identified. - Needs in terms of DRR integration into educational system has been identified. - New qualifications (formal and professional) at tertiary level have been identified. - Areas of integration and mainstreaming of disaster risk reduction, resilience and climate risk into existing curriculum at all levels have been identified. - Schools programmes have been identified. | All priority MS have been identified per REC All needs have been identified 1 per REC All MS All MS | G-5, F-6 | Dec 2022 Sep 2023 Sep 2023 Sep 2023 Sep 2023 |
| 1.7) New courses development and integration. | 1.7.1) Create network between “new” and “existing” DRR/CCA institutions. | National and regional | AUC, RECs, MS, Academic and research institutions | - Expansion of DRR/CCA knowledge networks in all regions (See 1.4). | One DRR/CCA knowledge network per REC | F-7, F-8 | Dec 2025 |
|  | 1.7.2) Development of new tertiary courses in disaster risk reduction, resilience and climate risk. | National | Academic institutions | - New tertiary qualifications in disaster risk reduction, resilience and climate risk have been developed and implemented. | One new qualification per REC. | G-5 | Dec 2024 |
|  | 1.7.3) Integrate disaster risk reduction, resilience and climate risk in existing curriculum at all levels. | National | MS | - Disaster risk reduction, resilience and climate risk is integrated in curriculum at all levels. | All MS | G-5 | Dec 2025 |
|  | 1.7.4) Develop schools programmes in disaster risk reduction, resilience and climate risk. | National | MS | - Schools programmes have been developed and implemented. | All MS | E-1 - E2, G-5 | July 2024 |
| 1.8) Biennial reporting on PoA | 1.8.1) Develop and maintain REC and AU specific websites for biennial reporting | Continental and regional | AUC, RECs | - Websites set-up and maintained. | All RECS and MS | G-5 | July 2022 |
|  | 1.8.2) Capacity development and technical support for regional and national data collection as per request. | Continental, Regional and national | AUC, UNDRR, RECs, UN agencies and International, regional and national organisations | - Capacity development interventions as requested. | 26 MS All MS | F-6 – F-8 | Dec 2022 Dec 2025 |
|  | 1.8.3) Convene biennial regional data review workshops. | Regional | AUC, RECs, UNDRR, MS | - Biennial data review workshops. | 1 workshop per REC. | All targets | Biennially |
|  | 1.8.4) Compile biennial regional reports. | Regional | RECs, MS, AUC, UNDRR, UN agencies and International, regional and national organisations | - Biennial REC reports. | 1 report per REC. | All targets | Biennially |
|  | 1.8.5) Compile policy briefs on regional reports. | Regional | RECs | - Policy briefs per REC. | 1 policy brief per REC. | All targets | Biennially |
|  | 1.8.6) Compile biennial continental and REC reports on progress made towards the implementation of the PoA for Africa and RECs. | Continental and regional | AUC, RECs, MS, UNDRR, UN agencies and International, regional and national organisations | - Biennial report on Africa. | 1 report for Africa. | All targets | Biennially |

| Priority 2: Strengthening disaster risk governance to manage disaster risk PoA Target 2: Increase integration of DRR in regional and national sustainable development, and climate change adaptation frameworks, mechanisms and processes PoA Target 5: Substantially increase the number of regional networks or partnerships for knowledge management and capacity development, including specialized regional centers and networks |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic areas of intervention | Key activities | Level of Implementation | Lead Institution/ Organisation | Results | Targets | PoA/SFDRR Targets to which they contribute | Timeframe |
| 2.1) Enhancing coordination mechanisms and DRR institutional capacities at continental, regional, sub-regional, national and sub-national level. | 2.1.1) Support to continental, regional, sub-regional, national and sub-national level organisations to accelerate risk informed development across and within sectors. | Continental, REC | AUC, UNDRR, AfDB, WB, RECs, MS | - DRR institutionalised in AUC and RECs - Capacity development schemes for training AUC, RECs and member states' staff operational. | All AUC and REC sectors One training intervention per AUC and REC per year | F-6, F-7 | Dec 2023 Annually |
|  | 2.1.2) Convene biennial Africa Regional Platform for DRR and AWGDRR. | Continental | AUC, UNDRR | - Biennial Africa Regional Platform is convened. - Biennial AWGDRR is convened. | One biennial platform One biennial AWGDRR. | All targets | Biennially |
|  | 2.1.3) Convene sub-regional DRR Platforms. | Regional | RECs, AUC, MS, Partner organisations | - Biennial REC DRR Platforms are convened. - Annual national DRR Platforms are convened and supported where needed. | One biennial REC platform One annual national DRR platform per MS.. | All targets | Biennially Annually |
| 2.2 Gender and Inclusion Mainstreaming in DRR | 2.2.1) Operationalisation of Gender and DRM Platform | Continental | AUC and Africa Risk Capacity (ARC) | - Increase in Gender sensitive DRM policies | One gender sensitive policy per MS | G-5, F-7 – F-8. | Dec 2022 |
|  | 2.2.2) Promote inclusion of women, youth, elderly and other vulnerable groups | Continental, Regional and National | AUC and AYAB, RECs and MS UN Agencies, International, regional and national organisations | - Women, youth and other vulnerable groups are members of DRR/M platforms and other DRR/M structures | 20% of platforms constitute women, youth and vulnerable groups | G-5, F-7 – F-8. | Dec 2023 |
|  | 2.2.3) Increase participation of women, youth and other stakeholders in DRR/M activities. | Continental, regional and national | AUC, RECs, MS, UNDRR, UN Agencies, International, regional and national organisations | - At least 50% of continental, regional and national DRR/M structures are women. - At least 25% of continental, regional and national DRR/M structures are youth. - At least 10% of continental, regional and national DRR/M structures are differently abled people. | 50% of continental, regional and national DRR/M structures are women. 25% of continental, regional and national DRR/M structures are youth. 10% of continental, regional and national DRR/M structures are differently abled people. | G-5, F-7 – F-8. | Dec 2025 |
|  | 2.2.4) Formulate gender-responsive DRR policies, strategies, plans and legal frameworks in line with the Sendai Framework, Paris Agreement, SDGs and the New Urban Agenda to ensure risk-responsive development. |  | MS, RECs, ICPs. MS, RECs, ICPs. | - RECs and MS disaster risk reduction and climate change adaptation policies includes a focus on gender, age and disability sensitivity. - New DRR, gender, age and disability policies at REC and MS level. | All MS | G-5; F-7 – F-8. | Nov 2024 Nov 2024 |
| 2.3) Transboundary disaster risk reduction | 2.3.1) Develop and implement a common understanding and approach to address regional and trans-boundary disaster risk concerns. | Regional | RECs, AUC, MS | - Annual regional risk reviews occur. - Cross boundary technical and scientific cooperation and information sharing is evident. - Common operating procedures are developed, shared, understood and used by all role-players. - Functioning multi-hazard early warning systems (see 4.2) | One risk review per REC Information sharing per REC via DRMICS (see 1.4.3) Common operating procedures per REC MHEWS per REC | G2 – G-5 | Annually July 2023 Dec 2023 Dec 2025 |
|  | 2.3.2) Establish regional frameworks for development of regional disaster-resilient health infrastructure and public health systems. | Continental and Regional | AUC (including CDC), RECs, MS | - Continental and Regional legal and statutory instruments for public health, where needed have been developed and implemented. - Regional sub-structures for public health have been established and are functioning. - Regional frameworks for disaster resilient health systems have been determined and enhanced. - Improved coordination and Trans-boundary management of public health risks. | Continental and Regional legal and statutory instruments for public health Regional sub-structures for public health in each REC Regional frameworks for disaster resilient health systems per REC. Trans-boundary management of public health risks as part of regional platforms. | E-1 – E2; F-1 – F8. | July 2022 July 2022 Dec 2023 July 2022 |
|  | 2.3.3) Develop and implement a voluntary Peer Review Mechanism (PRM) amongst RECs and MS. | Continental and Regional | AUC, RECs, MS | - Baseline study of PRMs for DRR has been undertaken. - The modalities/guidelines of the PRM have been adopted. - The PRM is implemented with evidence of at least five peer reviews per REC per year. - PRM reports are presented to the Ministerial Conference(s) | Baseline study Adopted guidelines Five peer reviews per REC per year PRM reports |  | March 2022 May 2022 July 2023 Annually |
| 2.4) Sub-national/Local level disaster risk reduction | 2.4.1) Establish/ strengthen multi-stakeholder and multi-sectoral national and local platforms that are gender responsive and inclusive, with the participation of local community representatives and other stakeholders. | National | MS, AUC, RECs, UNDRR, UN Agencies, International, regional and national organisations | - Reported increase in multi-stakeholder and multi-sectoral national and sub-national DRR/M platforms. | Annual national and sub-national DRR/M platforms in each MS | F1 - F5 | Dec 2022 Continuous |
|  | 2.4.2) Decentralise powers and resources to catalyse disaster risk reduction actions at the sub-national/ local level. | National | MS | - Increase in Sub-national/local bylaws, policies, plans and/or strategies which enforce DRR at sub-national/local level. - Reported increase in formal/statutory sub-national/local DRR/M structures. - Budgetary and resources allocation for DRR/M at local level (See 3.1 and 3.2) | 40 MS | E-2 | Dec 2024 Biennially Annually |
|  | 2.4.3) Develop the leadership and capacity of sub-national/local authorities to work with community structures, civil society and other local partners to advance local DRM. | National | MS | - Capacity development initiatives at sub-national/local level. - Annual advocacy programmes e.g. annual IDDRR Day are conducted at local levels. | Professional development courses in all MS. IDDRR Day in all MS | F-7 – F-8. | July 2023 Annually |
|  | 2.4.4) Increase participation of local actors, community based organisation(CBOs) traditional leadership in DRR/M activities. | National | MS | - Local actors are members of national DRM platforms and other national DRM structures. | At least 50% of local DRR/M structures are women. At least 25% of local DRR/M structures are youth. At least 10% of local DRR/M structures are differently abled people. | G-5; F-7 – F-8. | Dec 2025 |
| 2.5) Strategic, institutional, operational, conceptual and financial policy coherence among disaster risk reduction (DRR), climate change adaptation (CCA) and the Sustainable Development Goals (SDGs) | 2.5.1) Increase, assess, amend and update all outdated regional, national and local statutory and regulatory DRR frameworks, plans and strategies in line with the SFDRR and PoA, Paris Agreement, SDGs and the New Urban Agenda. | Continental, Regional and National | AUC, RECs, UNDRR MS, UN Agencies, International, regional and national organisations | - Substantial increase of sub-national DRR strategies and plans linked to sustainable development planning and resilience building. | All MS | E-1 – E-2 | Dec 2023 |
| 2.6) Mainstreaming DRR in development planning. | 2.6.1) Mainstream DRR and CCA in relevant AU policies, strategies, programmes and plans. | Continental | AUC, UN agencies | - Various entry points for policy coherence (such as resilience) have been identified and is being used to guide efforts. |  | E-1 – E-2; F-1 – F-7 | July 2022 |
|  | 2.6.2) Cross-sectoral stakeholder involvement and efficient knowledge management through improved data and information for policy coherence. |  | RECs, MS | - Formal and structured stakeholder interaction of practitioners (such as peer learning exchanges). | One peer learning exchange per REC | F-6 – F-7 | July 2024 |
|  | 2.6.3) Increase the integration of disaster risk reduction, sustainable development and climate change adaptation across sectors, emphasising local government. |  | RECs, MS | - Evidence of DRR and CCA mainstreaming across sectors and departments through development planning and programming. - DRR and CCA is integrated in local level development planning, linked to budget allocations based on risk assessment and analysis. | All RECs All MS | E-1 – E-2 | May 2023 Dec 2023 |
|  | 2.6.4) Development of Guidelines for mainstreaming DRR for integrating DRR, CCA and Sustainable Development | Regional, national | RECs, MS | - Guidelines for integrating CCA, DRR and Sustainable development are implemented. - Plan, strategies, programmes to use identified entry points for integration. | Guidelines Entry points identified | E-1 – E-2 | July 2023 July 2024 |
|  | 2.6.5) Enable and ensure the participation of various stakeholders from government, civil society, private sector and partnerships and networks in multi-stakeholder and multi-sectoral national and local platforms. | National | MS | - Involvement of multiple stakeholders in mainstreaming DRR, with evidence in development planning . | All MS | E-1 – E-2; F-7 | Continuous |
|  | 2.6.6) Raise risk awareness for understanding the link between DRR/CCA and development. | National | MS, RECs | - Risk assessments and analyses take into consideration aspects of environmental and social impact assessments, linked to development planning. - DRR/CCA and development integration is addressed in awareness and education. - Monitoring and evaluation of current and new development interventions are risk aware. | All RECs and MS | F4 – F-6 | Continuous Continuous Continuous |
|  | 2.6.7) Conduct budgeting and expenditure analysis to determine linkages between DRR, CCA and development. | National | MS, RECs, | - Tracking DRR and CCA funding at MS level. - Budgeting and expenditure analysis ensures the integration of DRR, CCA and development though various financial instruments. - Opportunities to use climate finances for DRR have been identified. | DRR budget line item in all MS and RECs | F-1 – F6 | Dec 2022 Dec. 2023 Dec 2023 |
|  | 2.6.8) Establish reporting mechanism for tracking DRR and CCA financing. | National | MS RECs, AUC, UN Agencies, International, regional and national organisations | - Reporting mechanism have been established. - Budget tagging system for DRR and CCA is established. | Budget reporting and tagging system in all MS. | F-1 – F6 | Dec 2024 |
|  | 2.6.9) Mobilise private and public resources for DRR, CCA and development integration. | National | MS, private sector | - Public and private resources mobilisation take into account/emphasise the linkages between DRR, CCA and development. | 10% increase in DRR/CCA funding. | F-1 – F6 | Dec 2023 |
|  | 2.6.10) Risk financing and transfers at source identifies DRR, CCA and development linkages. | Continental, Regional and National | AUC, RECs MS, ICPs | - Better coordination between donor/funders. |  | F-1 – F6 | Dec 2022 |
| 2.7) Regional networks/partnerships | 2.7.1) Identify networks/partnerships in DRR. | Continental, regional and national | AUC, RECs, MSMS | - Inventory of regional and sub-regional networks/partnerships - Inventory of PPP and private sector partnerships in DRR. | Inventory per REC | F-1 – F6, G-5 | July 2023 Dec 2022 |
|  | 2.7.2) Support and enhance existing networks/partnerships | Continental, regional and national | AUC, RECs, MS | - Sustainability of networks/partnerships | One DRR network per REC | F-1 – F7, G-5 | Dec 2023 |
|  | 2.7.3) Establish new networks/partnerships in DRR | Continental, regional and national | RECs, MS | - Number of new networks and partnerships established. |  | F-1 – F7 | Continuous |
| 2.8) Regional DRM centres | 2.8.1) Specialised regional technical, research and academic centres has been identified. | Regional | RECs | - Inventory of specialised regional technical, research and academic centres. - Identified priority centres. | Inventory per REC. Three per REC. | F-7 – F-8 | July 2022 Sept 2022 |
|  | 2.8.2) Support and enhance existing centres. | Regional | RECs, MS | - Programming and resources/budgetary support of existing centres in line with continental research and capacity development needs. | Budget per Centre | F-7 – F-8 | Dec 2022 |

| Priority 3: Investing in disaster risk reduction for resilience PoA Target 3: Substantially expand the scope and increase the number of sources for domestic financing in DRR |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic areas of intervention | Key activities | Level of Implementation | Lead Institution/ Organisation | Results | Targets | PoA/SFDRR Targets to which they contribute | Timeframe |
| 3.1) Continental and Regional Resilience funding mechanisms. | 3.1.1) Identify various funds on the continent and in RECs for DRR, CCA and resilience. | Continental | AUC, RECs | - Inventory of DRR/Resilience funds and their extent of funding. | Inventory per REC | F-1 – F6 | Dec 2022 |
|  | 3.1.2) Identify funding gaps. | Continental, Regional, national | AUC, RECs, MS | - Funding gaps in relation to DRR commitments and available resources at regional and national level has been determined. | All funding gaps identified. | F-1 – F6 | Jan 2023 |
|  | 3.1.3) Develop statutes and funding arrangements for sub-regional, RECs and continental funding mechanisms/funds. | Continental and Regional | AUC, RECs | - Continental and regional Resilience Funds are operational. - 1% of all regional development assistance budgets are allocated to DRR/M activities, programmes and projects. | One continental and one fund per REC | F-1 – F6 | Dec 2025 Dec 2024 |
| 3.2) Domestic and international funding for disaster risk reduction and resilience. | 3.2.1) Develop appropriate incentive frameworks that induce private investments and reduce vulnerability of populations most at risk (such as through social protection and insurance) | National | MS, ARC, AUC, private sector | - National incentive frameworks for private sector investment in DRR and resilience. - Social protection mechanisms are in place and operational. - Increased domestic allocations for DRR which can be tracked. - Insurance instruments in place for disaster risk transfer, sharing and retention. | All MS | F-1 – F6 | Dec 2024 Dec 2025 Dec 2023 Dec 2023 |
|  | 3.2.2) Improve the efficiency of allocating domestic resources invested in DRR across various programmes and sectors. | National | MS | - 1% of all national development budgets are allocated to DRR/M activities, programmes and projects. - National risk sensitive budget analysis. - Guidelines for investing in DRR across sectors based on risk sensitive budget analysis. - Local level investment in disaster risk reduction and climate change adaptation. | All MS | F-1 – F6; G-5 | Dec 2024 Dec 2023 July 2022 June 2023 |
|  | 3.2.3) Allocate and facilitate investment of dedicated, adequate and predictable resources and capacity to engage with communities at risk and implement local initiatives. | National | MS | - 1% of local level development budgets are allocated specifically for DRR/M activities, programmes and projects. | All MS | F-1 – F7 | Dec 2024 |
| 3.3) Domestic funding and funding channels | 3.3.1) Develop tools for MS self-assessment to determine current direct domestic sources of DRR funding (including development, disaster response and climate financing). | Continental and regional | AUC, RECs MS, Private sector, UN Agencies, International, regional and national organisations | - Sources of domestic DRR funding (such as national and sub-national budgets; national disaster (and response), contingency and resilience funds; bonds; reserves; insurance; taxes; debt/loan-financing; and social protection) have been identified. - Sub-national risk sensitive budget analysis. - Private sector sources of domestic DRR funding have been identified (such as PPPs, insurance, bonds, philanthropic and civil society contributions). | All MS | F-5 | Dec 2023 July 2024 Dec 2023 |
|  | 3.3.2) Include DRR as budget line item for tracking and monitoring. | National | MS, RECs | - DRR as budget line item for tracking and monitoring has been established (e.g OECD-DAC DRR marker). | All MS | F-1 – F7 | Dec 2022 |
| 3.4) Multi-sectoral domestic funding | 3.4.1) Identify (and exploit) alternative funding, entry points/channels for domestic funding for DRR. | National | MS, RECs, Private sector | - Alternative funding of DRR through all government departments, agencies’ and level of government’s budgets as well as DRR investments have been identified. - Opportunities for integrated DRR funding have been identified. - National sustainable development and climate change funding entry points which contribute to DRR have been identified. - Private sector involvement and leadership in business resilience and DRR. | All MS | F-1 – F7 | July 2023 July 2023 Dec 2022 Dec 2024 |
| 3.5) Alternative funding | 3.5.1) Decouple disaster response connotation to domestic DRR funding. | National | ICPs, RECs, MS | - DRR funding does not form part of/come from disaster response and rehabilitation funding. | All MS | F-1 – F7 | Dec 2025 |
|  | 3.5.2) Emphasise economic benefit of DRR | National | MS | - National DRR investment plans. - Increased private sector funding for resilience building. | All MS | F-1 – F7 | Dec 2023 Dec 2024 |
|  | 3.5.3) Adapt national and sub-national government, institutions, policies and plans to focus on direct DRR financing. | National | MS, Private sector | - Integrated development and operational planning with DRR at national and sub-national level. - Social protection mechanisms/social safety nets emphasise DRR through development. - Enhanced micro-finance and micro-insurance instruments for most at-risk groups. | 50% of all MS | E-1 – E-2; F-1 – F7 | March 2023 Dec 2024 July 2024 |
|  | 3.5.4) Engage/enhance national insurance instruments for DRR. | National | MS, Private sector | - Increase in the number of, and access to private and public sector insurance instruments. | 75% of all MS | F-1 – F7 | Dec 2024 |

| Priority 4: Enhancing disaster preparedness for effective response and to “Build back Better” in recovery, rehabilitation and reconstruction AND PoA Target 4: Increase the number of countries with, and periodically testing, risk-informed preparedness plans, and, response, and post-disaster recovery and reconstruction mechanisms |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic areas of intervention | Key activities | Level of implementation | Lead Institution /Organisation | Results | Targets | PoA/SFDRR Targets to which they contribute | Timeframe |
| 4.1) Preparedness and contingency planning | 4.1.1) Prepare/ update disaster preparedness and contingency plans at local, national and regional levels with a multi-stakeholder and multi-sectoral approach. | Regional and National | AUC, RECs, MS, UN agencies, private sector. | - Increase in number of regional disaster preparedness and response strategies. - Increase in continental and regional institutions, networks and forums for research, innovation and scientific solutions, incorporating traditional knowledge, for preparedness, response and recovery. - Annual preparation and update of contingency plans, in line with regional, national and local consultations. | One per REC | G-5 | July 2022 July 2023 Annually |
|  | 4.1.2) Comprehensive and accessible service and referral mechanisms to promote specific needs of women and children, the elderly, people with disabilities and other at-risk populations. | National | MS | - DRR/M mechanisms and services for at-risk groups are developed and implemented (e.g. at community centres, community groups, local DRM centres.) - DRM volunteers actively involved in preparedness services for at-risk groups. | All MS | G-5 | Dec 2024 Dec 2023 |
| 4.2) Establish continental MHEWS and Early Action Situation/Coordination centre. | 4.2.1) Establish situation room | Continental | AUC | - Continental MHEWS-EA Situation room operational | Continental MHEWS-EA Situation room at AUC level | G-5 | Dec 2022 |
|  | 4.2.2) Development of continental institutional frameworks | Continental | AUC | a) Institutional framework for MHEWS and Early Action | Framework | G-5 | Dec 2022 |
|  | 4.2.3) Development of SOPs. | Continental | AUC | - SOPs | All SOPS for MHEWS and EA | G-5 | Dec 2022 |
| 4.3) Multi-hazard Early Warning Systems | 4.3.1) Mechanisms for mutual cooperation and standardisation between regions and MS. | Regional and national | RECs, MS | - Regional mechanisms for mutual cooperation towards MHEWS between RECs and MS have been developed. - Development and implementation of MHEWS has been standardised across RECs and MS. - MHEWS are risk informed with linkages to national EWS. | One regional mechanism per REC | G-1, G-2 | July 2023 Dec 2024 July 2025 |
|  | 4.3.2) Strengthen multi-hazard early warning systems (MHEWS) to ensure last-mile accessibility by those most at-risk. | Regional and National | RECs, MS | - Increase in the number of regional and national MHEWS. - MHEWS ensures last mile accessibility for communities most at-risk. - MHEWS consider indigenous knowledge and systems. | One MHEWS per REC and MS | G-1 – G6 | Dec 2024 Dec 2023 Dec 2023 |
| 4.4) Response mechanisms and mechanisms for cooperation | 4.4.1) Develop effective regional response and recovery mechanisms to respond to and recover from trans-boundary disasters. | Regional | RECs, MS, AUC, ICPs, donors, private sector | - Regional emergency operations centres (EOCs) have been implemented. - Mutual aid agreements between RECs have been developed and operationalised. - Regional standards for response and recovery are developed and implemented (e.g. Incident Management/Command Systems linked to EOCs). - Joint disaster preparedness and response interventions among MS and RECs. - Annual testing of preparedness plans, response and post-disaster recovery mechanisms. - Partnerships with donors, ICP and the private sector to strengthen national post-disaster response management capacities. - Regional transit of humanitarian resources, including stockpiling, is identified and developed. - Development of regional capacity in maritime disaster response and preparedness, including regional Search and Rescue drill exercises for maritime incidents | EOCs in all RECs | G-4 – G6 | Dec 2022 Dec 2023 July 2024 July 2024 Annually Dec 2023 June 2024 Dec 2023 |
|  | 4.4.2) Establish and strengthen national emergency preparedness, response and recovery support and coordination mechanisms, capacities and facilities, including coordination centres. | National | MS | - Emergency communication systems and channels of communication established (national to local level). - Common Incident Management/Command System (IMS) has been developed. - Multi-sectoral and stakeholder capacity development in IMS. - Annual simulation exercises at national level coordinated by IMS. - 10% of disaster response funds allocated towards DRR. | All MS | G-5 | Dec 2024 Dec 2023 Dec 2023 Annually Dec 2022 |
|  | 4.4.3) Establish and strengthen multidisciplinary local emergency preparedness, response and recovery mechanisms. | National | MS | - National IMS standard is implemented at sub-national and local level. - Annual simulation exercises at local level coordinated by IMS. - Sub-national disaster risk management plans include early warning, response coordination, evacuation plans, stockpiling of necessary materials to implement rescue and relief activities. - Local systems of community disaster risk management volunteers are established. - Active involvement of volunteer corps in DRR, disaster preparedness, response, and recovery. | All MS | G4 – G6 | Dec 2023 Annually Dec 2023 July 2023 Dec 2023 |
|  | 4.4.4) Promote the use of indigenous knowledge, institutions and practices in needs-based preparedness planning and response management. | National | MS | - Evidence of the use of indigenous knowledge in early warning, preparedness planning and response. | 75% of all MS | G-4 | July 2023 |
| 4.5) Risk sensitive post-disaster recovery and reconstruction and “Build Back Better” | 4.5.1) Develop national building codes, urban development plans and retrofitting plans in line with disaster risk profile. | National | MS | - National enforced building codes. | 75% of all MS | G-5 | Dec 2023 |
|  | 4.5.2) Develop and implement post-trauma programmes. | National | MS | - Post-trauma programmes focussing on at-risk groups. | All MS | G-4, G5 | Dec 2022 |
|  | 4.5.3) Implement Post-disaster reconstruction programmes that focus on building resilience livelihoods. | National | MS | - Enhanced resilience through reconstruction programmes. | All MS | G-4 | July 2024 |
|  | 4.5.4) Foster Public-private-partnerships for recovery and reconstruction. | National | MS, private sector | - Private sector involvement in recovery and reconstruction. - Partnerships promote inclusive recovery and reconstruction. | All MS | G-5 | Dec 2023 Dec 2023 |
|  | 4.5.5) Mainstream ecosystems-based approaches through transboundary cooperation for resilience building. | Regional and national | MS, RECs | - Eco-DRR in reconstruction, recovery and development planning. | 75% of all MS | G-5 | July 2023 |