| PART 1 - Basic Information (To be completed by the supervisor) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NAME (LAST, FIRST) Sajadul | TITLE OF POST UNDRR Consultant |  | DUTY STATION (Country) Niger |  | RECRUITING AGENCY UNDRR |  | Host AGENCY ACMAD |
| FUNCTION (a brief description of key tasks) Facilitating establishment of continental impact based early warning system by improving risk understanding, establish situation room at AUC, ACMAD and RECs in collaboration with other consultants |  |  |  | PERIOD OF DEPLOYMENT: FROM: xxx 2021 TO: September 2021 |  |  |  |
| PART 2 - Key Assignments and Achievements (As stated in the terms of reference. |  |  |  |  |  |  |  |
| Planned key assignments and outputs |  | Achievements |  |  |  | ACMAD's assessment or comment |  |
| - Prepare continental watch. - Prepare situation report on hazards that occurred - coordinate data exchange at continental and regional levels |  | Draft prepared and under review Template for the report provided, data collection supported and review of the situation report regular A status on data exchange done at ACMAD |  |  |  | Need to accelerate review and finalization, the watch should help locate hazards and evaluate potential impacts and expected response measure for resilience Good performance The consultant should accelerate by contacting the WMO Information System Global centre in Casablanca on which ACMAD should be connected for data exchange to collect metadata catalogue template for WIS, fill products selected from ACMAD data catalogue in MyDEWETRA, map new data exchange set up at ACMAD with Mydewetra and WIS |  |
| - Design ACMAD watch centre with SOPs |  | Not done |  |  |  |  |  |
| - Install mydewetra at ACMAD for data exchange |  | No progress pending on infrastructure to be installed in ACMAD situation room |  |  |  | Accelerate iterations with CIMA to make progress on this task |  |
| - Work with ACMAD to integrate forecasts products |  | Data collection done, continental watch template under preparation, data collection and review of draft continentals watch regular |  |  |  | Support further finalization of watch final template with expected weather/climate phenomena, hazards outlook, potential impacts, response measures ( an example from IPCC reference reports was provided to Sajadul to facilitate his work) |  |
| 7- provide input to AUC situation room and situation report |  | Supported occasional situation report when hazard occurs |  |  |  | done |  |
| 2 out of 7 assignments are done |  |  |  |  |  |  |  |