AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA

# ADD PROJECT LOGO

# Detailed Work Plan

Deliverable D8.2

Lead Beneficiary: WMO

ADD Authors

Co-Authors: ADD

ADD PROJECT WEBSITE LINK

Document Information

Grant Agreement:	ADD

Project Title:		ADD

Project Acronym: 	ADD

Project Start Date:	ADD

Related work package:	ADD

Related task(s):		ADD

Lead Organisation: 	ADD

Submission date:	ADD

Dissemination Level:	ADD

History

| Date | Submitted by | Reviewed by | Version (Notes) |
| --- | --- | --- | --- |

ADD PROJECT PRESENTATION

ADD PROJECT PRESENTATION

ADD PROJECT PRESENTATION

About ADD PROJECT NAME

Coordinator contact

ADD

Table of Content

1	Executive Summary	3

2	List of the main acronyms used in this document	3

3	Description of WP 7 “Capacity development” activities	5

3.1	Task 7.1.: Assess capacity development needs and review and upgrade curricula	5

3.2	Task 7.2:  Develop and test training materials	6

3.3	Task 7.3:  Develop online resources	6

3.4	Deliverables of WP 7	7

3.5	Milestones of WP7	7

3.6	Interaction with other WPs	8

3.7	Risks of WP7	8

Annex

# Executive Summary

This deliverable is the project work plan. WPs were divided into several actions that all lead to the project objectives. There is always at least one responsible appointed for an action. This document shall be used by the coordination team to follow-up the project activities and also by FOCUS-Africa consortium. This document shall be updated along the project duration in case of delay, unforeseen risks, etc. in the action implementation.

# List of the main acronyms used in this document

| AB | Advisory Board |
| --- | --- |
| DoA | Description of Action |
| GA | Grant Agreement |
| MS | Milestone |
| Tbd | to be determined |
| WP WPL WS | Work Package Work Package Leader Workshop |

# Description of WP 7 “Capacity development” activities

Start date: 01/09/2020; End date: 31/08/2024

Work Package Leader: Andre Kamga (ACMAD)

Co-Leader: Roberta Boscolo ( WMO), Alberto Troccoli(WEMC),  Raul Marcos ( BSC),    Nicolas Fournier (MO), Matello Del Aqua (SSAA),    ADD Name (UTC)

This work package aimed at strengthening NMHSs and other  climate services providers capacity using latest advances in science and technology. It will address:

- Assess training needs

- Review and upgrade existing curricula on data, monitoring, forecasting and climate change detection and scenario development

- Develop and test new materials with RCOFs and intra ACP GFCS initiatives

## Task 7.1.: Assess capacity development needs and review and upgrade curricula

Start date: ADD End date: ADD

Task Leaders: Andre Kamga (ACMAD)

Contributors: Raul Marcos (BSC), Roberta Boscolo (WMO), Nicolas Fournier (MO),  ADD NAME (UCT)

The aim of this task is to collect and analyse available curricula and material developed and used for RCOFs in the SADC region and other regions with common climate processes and phenomena.  The analysis includes clustering of materials per knowledge requirements for each competency area described in the WMO competency framework for climate services, identifying gaps in the curriculum and materials using the performance criteria to be met by each participant exposed to the available material. Based on new findings and understanding, gaps in materials and curriculum will be filled trough a review and update process.  To implement this task, the following actions will be undertaken:

| Actions | Start Date | Due Date | Responsible |
| --- | --- | --- | --- |
| - Action 1: Collection of curricula and training materials | 01/09/2020 | 30/03/2021 | ACMAD&MO |
| - Action 2: Putting together materials relevant for each WMO climate service competency area and relevant knowledge requirement | 01/12/2020 | 30/05/2021 | ACMAD&WMO |
| - Action 3: Identification and analysis of gaps in the materials/curricula based on recent advances in science and technology | 01/02/2021 | 31/07/2021 | ACMAD&MO&UCT |
| - Action 4: Provision of an update plan for material/curricula using advances in science and technology | 01/03/2021 | 30/08/2021 | ACMAD&MO&UCT&BSC |
| - Action 5: Drafting, reviewing and finalization of the report on gaps and plan for capacity development | 01/04/2021 | 30/09/2021 | ACMAD&MO |

## Task 7.2:  Develop and test training materials

Start date: 01/09/2021 End date: 31/08/2023

Task Leaders: Andre Kamga(ACMAD)

Contributors: Raul Marcos (BSC), Roberta Boscolo (WMO), Nicolas Fournier (MO), Alberto Troccoli (WEMC), Matteo dell’Acqua (SSSA)   ADD NAME (UCT)

The aim of this task is to develop new or upgrade training material for climate services. Research findings, understanding of climate from FOCUS-Africa research and other climate science efforts will be reviewed and included in upgrades or new developments. Stakeholder workshops of WP 7 will be mechanism to share information on the material and test online training materials, collect feedback for further improvements. A specific test with the case study 3 in Mozambique with provide training materials using inclusive and participatory approaches on climate services for food security early warning and adaptation.    To complete this task, the following set of actions will be implemented:

| Actions | Start Date | Due Date | Responsible |
| --- | --- | --- | --- |
| - Action 1: Review of FOCUS-Africa findings | 01/09/2021 | 30/04/2022 | ACMAD&MO |
| - Action 2: Provision of training materials on seasonal forecasting by WP 4 | ADD | ADD | ADD |
| - Action 3: Provision of training material on the predictability of variables, features and phenomena for seasonal, decadal and multidecadal timescales in the region | 01/09/2021 | 31/12/2023 | ACMAD&BSC |
| - Action 4: Provision of training material to use seasonal forecasts and projected data for local adaptation on crop types | 01/07/2021 | 30/04/2022 | SSSA&ACMAD |
| - Action 5: Provision of climate change training material and review the proposed updates | 15/03/2021 | 20/11/2021 | UCT&ACMAD |
| - Action 6: test and reflect on the training materials with case study 3 with participation and inclusion of all stakeholders of the case study | 01/01/2022 | 20/07/2024 | WMO&ACMAD&WEMC |
| - Action 7: Collection of materials tested | 15/03/2021 | 20/11/2021 | UCT&ACMAD |
| - Action 8: Report on the materials available highlighting related competencies and expected performance to be built | 01/01/2022 | 20/07/2024 | WMO&ACMAD |

## Task 7.3:  Develop online resources

Start date: 01/09/2022 End date: 31/08/2024

Task Leaders: Andre Kamga(ACMAD)

Contributors: Raul Marcos (BSC), Roberta Boscolo (WMO), Nicolas Fournier (MO), Alberto Troccoli (WEMC), ADD NAME (UCT)

The aim of this task is to provide the develop training materials online and available to the wider community of climate service providers and users across Africa. This effort will sustain future capacity development initiatives in Africa with materials available online to organize and run training workshops and future Regional Climate Outlook For a (RCOFs) training sessions.

| Actions | Start Date | Due Date | Responsible |
| --- | --- | --- | --- |
| - Action 1: Online materials content Definition | 01/09/2022 | 30/04/2023 | ACMAD&WMO |
| - Action 2: Online material content design | 01/10/2022 | 30/03/2024 | ACMAD&MO |
| - Action 3: Online content development | 01/11/2022 | 30/04/2024 | ACMAD&WEMC |
| - Action 4: online content development for seasonal forecasting | 01/11/2022 | 30/09/2023 | ACMAD&BSC |
| - Action 5: Development of online material for climate change scenarios | 01/12/2022 | 31/12/2023 | ACMAD&UCT |
| - Action 6: Collection and upload of materials online | 15/03/2021 | 20/11/2021 | UCT&ACMAD |
| - Action 7: Report on the online materials available and other capacity development results | 01/01/2024 | 20/05/2024 | WMO&ACMAD |

## Deliverables of WP 7

| Number | Title | Due Date | Responsible |
| --- | --- | --- | --- |
| D7.1 | Needs and plan for capacity development | 01/09/2021 | Andre Kamga (ACMAD) |
| D7.2 | Online resources and module | 01/09/2023 | Andre Kamga (ACMAD) |
| D7.3 | Final report on capacity building results | 31/08/2024 | Andre Kamga (ACMAD |

## Milestones of WP7

| Number | Title | Verification mean | Due Date | Responsible |
| --- | --- | --- | --- | --- |
| MS1 | Inputs collected on the needs at first stakeholder workshop | Workshop’s minutes | 31/12/2020 | ACMAD |
| MS2 | Draft training materials presented for feedback at the Second stakeholder workshop | Workshop’s minutes | 31/08/2021 | ACMAD |
| MS3 | Roll out of training at Third workshop | Workshop’s minutes | 30/04/2022 | ACMAD |
| MS4 | Roll out of online training course | Final report | 30/10/2023 | ACMAD |

## Interaction with other WPs

| Number | Interaction description | Responsible |
| --- | --- | --- |
| WP1 | Task 1.1. Stakeholder workshop will facilitate training needs and plan preparation, training materials quality and value improvements Task 1.3 Training material will be used in workshops, fora and meeting linked to this task | WMO |
| WP3 | Task 3.1 Training materials on the drivers and predictors of seasonal climate variability will facilitate analysis of predictability in this task Results from this Work package tasks will be considered in training material development | MO |
| WP4 | Task 4.1 Results from this task will support training material development on seasonal forecasts quality assessment. The review of existing methodologies at SARCOF and SWIOCOF for quality assessment will provide a reference base to develop better quality assessment methods and tools in this task. Results from this work package will provide inputs to new or updated training materials on methods, tools for forecasts verification, downscaling and other direct model outputs post processing for value addition | BSC |
| WP5 | Task 5.1 and 5.2 Results from these tasks will provide inputs to training material on tailoring of forecasts products The online training materials will facilitate task 5.3 On the prototypes delivery to the wider community | WEMC |
| WP6 | Methods and tools for socio economic impact assessment of prototypes will be included in the training materials for future training on valuation of NMHSs and RCCs products and services | LGI |

## Risks of WP7

Risks (number, description, risk-mitigation), probability (1=low; 4=high) that the risk occurs and impact (1=low; 4=high) if the risk occurs. Other risks (not in GA) can be added so they can be followed during the project. Risk mitigation: P=preventive actions / C=contingency actions.

| Number | Risk description | Risk mitigation | Proba | Impact |
| --- | --- | --- | --- | --- |
| 1 | COVID 19 may reduce interactions between stakeholders needed for baseline data collection and feedback sharing on new materials | P: organize many short online events C: share documents through the project website and exchange more via emails | 4 | 3 |
| 2 | Internet brownouts and slow connection limiting effectiveness of online events and real time exchanges | P: contact more than one internet service provider C: monitor ISPs performance and book high banwidth ahead of events | 3 | 2 |