Good morning everybody,

A brief overview of the outcomes of our monthly meeting (can also be found in October monthly report on FLEXX):

- Introduction of Mercy Macharia (SSSA), Piotr Wolski (UCT) and Jaume Ramon (BSC)

- Mercy provided some information on the recent trip to Mozambique with WMO/LGI. The main outcome from the local farmers is the need of robust rainfall onset forecast

- Hamid (WMO) provided some information ion the recent WMO State of Africa report: Climate change triggers mounting food insecurity, poverty and displacement in Africa | World Meteorological Organization (wmo.int)

- Task 3.3 (MO, Aug 22) ) Tair/rain extreme analysis for present-day in RCMs/GCMs over SADC:

  - MO is planning to analyse observed data and present-day simulations from CMIP6, CORDEX-CORE and CP4A

  - The analysis is currently planned to use approach of our colleague E. Kendon (Figures 5-6; Kendon et al. 2019: Enhanced future changes in wet and dry extremes over Africa at convection-permitting scale | Nature Communications)

  - It was also discussed to include the analysis of the CCAM downscaled projections as it will also contribute to Task 4.2 (August 2022). UCT and WITS will support MO to undertake this during 2022.

  - EDF mentioned the need of bias corrected / optimised climate projections for the Malawi case study. This will be tackled in Tasks 4.2, 4.3 and 4.4 with the support of UCT/WITS/BSC/MO.

- Task 3.2 (WITS, Feb 2022)

  - Chou Chihchung (BSC) presented some analysis of ECMWF SEAS5 forecasts for the time period 1981-2016. He analysed its predictability based on the indices Nibo3.4 and ATL3 corroborating the stronger influence of the ENSO one for SADC.

- Next meeting - Friday 26th November:

  - SSSA Task 3.2 presentation

  - Task 3.2 status? Needs extension?

Regards,

Nicolas

http://154.66.220.45:8080/thredds/fileServer/FIT/BRIEFING/briefing.pdf

http://154.66.220.45:8080/thredds/fileServer/ACMAD/WWFD/verificationservice/Forecast_Verification.pdf

http://154.66.220.45:8080/thredds/fileServer/RDT/20211019/202110190830/index.html

119 mm on October 21 2021 in Douala Cameroon

http://154.66.220.45:8080/thredds/fileServer/ACMAD/WWFD/verificationservice/OBS/RR24.html