EWS Expertise to support

Multi Hazards Early Warning System (MHEWS)

In the

African Center of Meteorological Applications for Development (ACMAD)

Inception Report

Output 1

Submitted by

Maixent Olivier Claver KAMBI, EWS Expert in ACMAD

october 2022

Table of Contents

1.	LIST OF ACRONYMES	3

2.	Overview of the Consultancy	5

3.	METHODOLOGY AND TOOLS	5

4.	ANNEXES	6

ANNEXES

Annex 1 Deliverables Schedule	6

Annex 2 Workplan (Tasks, Deliverable/milestones, URL)	7

# LIST OF ACRONYMES

| ACMAD | African Centre of Meteorological Applications for Development |
| --- | --- |
| AMHEWAS | Africa Multi-Hazard Early Warning and Early Action System |
| AUC | Africa Union Commission |
| DOC | Disaster Operations Centre |
| DRM | Disaster Risk Management |
| DRR | Disaster Risks Reduction |
| GFCS | Global Framework for Climate Service |
| GIS | Geographic Information System |
| GMAS | Multi-hazard Alert System |
| GPDRR | Global Platform for Disaster Risk Reduction |
| ICPAC | IGAD'S Climate Prediction and Applications Centre |
| IFCR | International Federation of Red cross and Red Crescent |
| IGAD | Intergovernmental Authority on Development |
| IN-MHEWS | International Network on Multi Hazards Early Warning Systems |
| LDC | Least Developed Countries |
| MHEWAS | Multi-hazard Early Warning System |
| MHEWC | Multi-Hazard Early Warning Conference |
| MHEWS | Multi-Hazard Early Warning System |
| myDEWETRA | (Italian acronym) Open-source web-based system for real-time monitoring and forecasting of natural hazards like floods, landslides, and wildfires. |
| NMHS | National Meteorological and Hydrological Services |
| OCHA | Office for the Coordination of Humanitarian Affairs |
| REC | Regional Economic Communities |
| RCC | Regional Climate Center |
| SFDRR | Sendai Framework for Disaster Risk Reduction |
| SIDS | Small Island Developing States |
| SOP | Standard Operating Procedures |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNDRR | United Nations Office for Disaster Risk Reduction |
| UNDP | United Nations Development Programme |
| WCASP | World Climate Applications and Services Programme |
| WMO | World Meteorological Organization |
| WMO-WIS | WMO Weather Information System |

# Overview of the Consultancy

UNDRR partners with the AU Commission, ACMAD, RECs, Member States and other partners to mobilize resources for the establishment of Multi-Hazard Early Warning System (MHEWS) supported by the overnment of Italy under the project entitled "Establishment of the impact-based early warning for early action and trans-boundary risk management function of the African Union". The initiative aims at building the capacity of the African Union Commission, African Centre of Meteorological Application for Development (ACMAD), Regional Economic Communities (RECs) and Member States to effectively collect, exchange and analyse Risk information relevant to impact based Early Warning Systems (EWS) for Early Action and Trans-boundary Risk Management.

In accordance with the Term of Reference, the expert will accountable for technical assistance to develop and operationalize mergency preparedness and response Early Actions in the context of transboundary risk management, in ensuring a seamless implementation of the MHEWS. This exercise will consist of seven major points:

- Install and maintain the operations of the MyDEWETRA platform at ACMAD;

- Support ACMAD/WIS/DCPC including through updating of the web portals, installation and operation of knowledge management systems, developing products catalogue specifically to facilitate interactions between ACMAD and the situation rooms at AUC and REC levels;

- Implement cloud-based data processing and data archiving and sharing platforms;

- Design applications and web servers for data exchange;

- Integrate ACMAD products in the MyDEWETRA platform;

- Design and establish a geospatial portal;

- Support the establishment of dashboards and other applications facilitating access to and exchange of data

# METHODOLOGY AND TOOLS

The outcome of the mission is an operationalized Emergency Preparedness Plans and Early Response Actions for Transboundary Risk Management, that contribute to better understanding of the potential impacts of disasters, promote and facilitate impact-based advisories, watches, and warnings, in direct collaboration with DRR experts at the situation Room at the AUC and at the RECs.

For the success of this mission, it will require a methodology articulated around a review of the various existing data exchange platforms, consultations with the ACMAD team.

# ANNEXES

Annex 1 Deliverables Schedule

| Deliverables | Time frame |
| --- | --- |
| 1. Inception report including the workplan, |  |
| 2. Activities schedule |  |
| 3. website status report, catalogue available | 01/10/2022 to 26/11/2022 |
| 4. Products in WIS format available | 28/10/2022 to 08/11/2022 |
| 5. Inventory report | 19/10/2022 to 26/10/2022 |
| 6. Product report on the platform | 08/11/2022 to 16/11/2022 |
| 7. Report on the use of the site | 11/11/2022 to 12/11/2022 |
| 8. Report on the geoportal | 17/11/2022 to 23/11/2022 |
| 9. Monthly and end reports | 24/11/2022 to 26/11/2022 |

Annex 2 Workplan (Tasks, Deliverable/milestones, URL)

| Work plan of Mr Maixent KAMBI - UNDRR Consultant (To be executed and implemented with the frank and good collaboration of the ACMAD team) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Deliverables | Activities | Tasks | Scheduled dates for execution |  |
|  |  |  | Start date | End date |
| Inception report including workplan and schedule | Establishment of the workplan for the execution of the following activities and tasks | • exchanges with collaborators | 19/10/2022 | 23/10/2022 |
| website status report, catalogue available | Support ACMAD/WIS/DCPC, including updating web portals, installation and operation of knowledge management systems, development of a product catalogue specifically to facilitate interactions between ACMAD and Situation Rooms at AUC and REC levels | • review, analyze, determine weaknesses and errors, correct the different pages of the website, fill in the website tracking table with the URL to each page, the weaknesses and errors found on the page, the corrections made to the page, develop the site map | 04/11/2022 | 05/11/2022 |
|  |  | • Organize the pages of the site into rubrics | 07/11/2022 | 08/11/2022 |
|  |  | • Updating the website product section | 01/10/2022 | 26/11/2022 |
|  |  | • develop the ACMAD product catalogue in collaboration with the different experts | 01/11/2022 | 03/11/2022 |
| Products in WIS format available | Format ACMAD products in WIS format departments, implement the data center | • elaborate the scripts, format the products in geotiff, csv, json, jpeg or gif, visit the EUMETSAT and ECMWF data center, build the front page of the ACMAD data center, build the products catalogue page on the data center, create the access links and download the products from the data center, install and configure WIS, update the catalogue and metadata on the WIS, produce the administration and maintenance manual with update of DCPC products (RCC and RSMS severe weather) on the WIS, visualize and update the RCC and RSMC severe weather catalogues in the data center | 28/10/2022 | 08/11/2022 |
| Inventory report | Getting to know the MyDEWETRA platform | • inventory of existing products (catalogue of ACMAD products currently on MyDewetra as well as those to be added) | 24/10/2022 | 26/10/2022 |
|  |  | • getting to know the application or configuration of the MyDEWETRA platform accessible through ACMAD data center | 19/10/2022 | 25/10/2022 |
| Product report on the platform | Integration of ACMAD products into the MyDEWETRA platform | • integrate inventories and catalogs of identified products into MyDEWETRA | 08/11/2022 | 10/11/2022 |
|  |  | • format products, import and display in MyDEWETRA format | 12/11/2022 | 16/11/2022 |
| Report on the use of the site | Report presenting stakeholder/user comments and their analysis | • installing monitoring Tools | 04/11/2022 | 05/11/2022 |
|  |  | • elaborate visitor statistics, analyze in the report | 11/11/2022 | 12/11/2022 |
| Report on the geoportal | Design and implement a Geoportal | • inventory of the existing situation at ACMAD then design the hardware and software architecture, choose the prototype | 17/11/2022 | 18/11/2022 |
|  |  | • develop the plan for the design, development, testing and operationalization of the Geoportal | 18/11/2022 | 23/11/2022 |
|  |  | • implement the plan in collaboration with other experts | 18/11/2022 | 23/11/2022 |
| Monthly and end reports |  |  | 24/11/2022 | 26/11/2022 |