EWS Expertise to support

Multi Hazards Early Warning System (MHEWS)

In the

African Center of Meteorological Applications for Development (ACMAD)

Inception Report

Output 1

Submitted by

Maixent Olivier Claver KAMBI, EWS Expert in ACMAD

october 2022

Table of Contents

1.	LIST OF ACRONYMES	3

2.	Overview of the Consultancy	5

3.	METHODOLOGY AND TOOLS	5

4.	ANNEXES	6

ANNEXES

Annex 1 Deliverables Schedule	6

Annex 2 Workplan (Tasks, Deliverable/milestones, URL)	7

# LIST OF ACRONYMES

| ACMAD | African Centre of Meteorological Applications for Development |
| --- | --- |
| AMHEWAS | Africa Multi-Hazard Early Warning and Early Action System |
| AUC | Africa Union Commission |
| DOC | Disaster Operations Centre |
| DRM | Disaster Risk Management |
| DRR | Disaster Risks Reduction |
| GFCS | Global Framework for Climate Service |
| GIS | Geographic Information System |
| GMAS | Multi-hazard Alert System |
| GPDRR | Global Platform for Disaster Risk Reduction |
| ICPAC | IGAD'S Climate Prediction and Applications Centre |
| IFCR | International Federation of Red cross and Red Crescent |
| IGAD | Intergovernmental Authority on Development |
| IN-MHEWS | International Network on Multi Hazards Early Warning Systems |
| LDC | Least Developed Countries |
| MHEWAS | Multi-hazard Early Warning System |
| MHEWC | Multi-Hazard Early Warning Conference |
| MHEWS | Multi-Hazard Early Warning System |
| myDEWETRA | (Italian acronym) Open-source web-based system for real-time monitoring and forecasting of natural hazards like floods, landslides, and wildfires. |
| NMHS | National Meteorological and Hydrological Services |
| OCHA | Office for the Coordination of Humanitarian Affairs |
| REC | Regional Economic Communities |
| RCC | Regional Climate Center |
| SFDRR | Sendai Framework for Disaster Risk Reduction |
| SIDS | Small Island Developing States |
| SOP | Standard Operating Procedures |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNDRR | United Nations Office for Disaster Risk Reduction |
| UNDP | United Nations Development Programme |
| WCASP | World Climate Applications and Services Programme |
| WMO | World Meteorological Organization |
| WMO-WIS | WMO Weather Information System |

# Overview of the Consultancy

UNDRR partners with the AU Commission, ACMAD, RECs, Member States and other partners to mobilize resources for the establishment of Multi-Hazard Early Warning System (MHEWS) supported by the overnment of Italy under the project entitled "Establishment of the impact-based early warning for early action and trans-boundary risk management function of the African Union". The initiative aims at building the capacity of the African Union Commission, African Centre of Meteorological Application for Development (ACMAD), Regional Economic Communities (RECs) and Member States to effectively collect, exchange and analyse Risk information relevant to impact based Early Warning Systems (EWS) for Early Action and Trans-boundary Risk Management.

In accordance with the Term of Reference, the expert will accountable for technical assistance to develop and operationalize mergency preparedness and response Early Actions in the context of transboundary risk management, in ensuring a seamless implementation of the MHEWS. This exercise will consist of seven major points:

- Install and maintain the operations of the MyDEWETRA platform at ACMAD;

- Support ACMAD/WIS/DCPC including through updating of the web portals, installation and operation of knowledge management systems, developing products catalogue specifically to facilitate interactions between ACMAD and the situation rooms at AUC and REC levels;

- Implement cloud-based data processing and data archiving and sharing platforms;

- Design applications and web servers for data exchange;

- Integrate ACMAD products in the MyDEWETRA platform;

- Design and establish a geospatial portal;

- Support the establishment of dashboards and other applications facilitating access to and exchange of data

# METHODOLOGY AND TOOLS

The outcome of the mission is an operationalized Emergency Preparedness Plans and Early Response Actions for Transboundary Risk Management, that contribute to better understanding of the potential impacts of disasters, promote and facilitate impact-based advisories, watches, and warnings, in direct collaboration with DRR experts at the situation Room at the AUC and at the RECs.

For the success of this mission, it will require a methodology articulated around a review of the various existing data exchange platforms, consultations with the ACMAD team.

# ANNEXES

Annex 1 Deliverables Schedule

| Deliverables | Time frame |
| --- | --- |
| 1. Inception report including the workplan, |  |
| 2. Activities schedule |  |
| 3. Rapport sur l'état de site, catalogue disponible | 01/10/2022 to 26/11/2022 |
| 4. Produits au format WIS disponible | 28/10/2022 to 08/11/2022 |
| 5. Rapport de l’Etat de lieu | 19/10/2022 to 26/10/2022 |
| 6. Rapport sur les produits sur la plateforme | 08/11/2022 to 16/11/2022 |
| 7. Rapport sur l'utilisation du site | 11/11/2022 to 12/11/2022 |
| 8. Rapport sur le geoportail | 17/11/2022 to 23/11/2022 |
| 9. Rapports mensuels et de fin | 24/11/2022 to 26/11/2022 |

Annex 2 Workplan (Tasks, Deliverable/milestones, URL)

| Plan de travail de Mr Maixent KAMBI - Consultant UNDRR (A exécuter et mettre en œuvre avec la franche et bonne collaboration de l'équipe ACMAD) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Delivrables | Activités | Taches | Dates prevues pour l'exécution |  |
|  |  |  | Date de Début | Date de Fin |
| Rapport de démarrage comprenant le workplan, et chronogramme | Etablissement du plan de travail pour l'exécution des activités et taches ci-dessous | • échanges avec les collaborateurs | 19/10/2022 | 23/10/2022 |
| Rapport sur l'état de site, catalogue disponible | Soutenir l'ACMAD/WIS/DCPC, notamment par la mise à jour des portails Web, l'installation et l'exploitation de systèmes de gestion des connaissances, l’élaboration d'un catalogue de produits spécifiquement pour faciliter les interactions entre l'ACMAD et les salles de situation aux niveaux de la CUA et des CER | • passer en revue, analyser, déterminer les faiblesses et erreurs, corriger les différentes pages du site web, remplir le tableau de suivi du site avec l’url vers chaque page, les faiblesses et erreurs constates sur la page, les corrections apportées à la page, élaborer le plan du site | 04/11/2022 | 05/11/2022 |
|  |  | • Repartir les pages du site dans les rubriques | 07/11/2022 | 08/11/2022 |
|  |  | • Mettre à jour du site web volet produits | 01/10/2022 | 26/11/2022 |
|  |  | •élaborer le catalogue des produits ACMAD en collaboration avec les experts des différents | 01/11/2022 | 03/11/2022 |
| Produits au format WIS disponible | Formater les produits d’ACMAD au format WIS départements, mettre en place le data centre | • élaborer le scripts , formater les produits en geotiff, csv, json, jpeg ou gif, visiter le data centre EUMETSAT et CEPMMT, construire la page de garde du DATA centre ACMAD, monter la page catalogue des produits sur le data centre , créer les lien d’accès et téléchargement des produits à partir du data centre , installer et configurer WIS, mettre à jour le catalogue et metadata sur le WIS , produire le manuel d’administration et de maintenance avec mise à jour des produits DCPC ( RCC et RSMS severe weather) sur le WIS, faire visualiser et mettre à jour les catalogues RCC et RSMC severe weather dans data centre | 28/10/2022 | 08/11/2022 |
| Rapport de l’Etat de lieu | Mise en main de la plateforme MyDEWETRA | • état de lieu de l’existant (catalogue des produits de l’ACMAD actuellement sur MyDewetra ainsi que ceux à y mettre | 24/10/2022 | 26/10/2022 |
|  |  | • prise en main de l’application ou configuration de la plateforme MyDEWETRA accessible à travers ACMAD data centre | 19/10/2022 | 25/10/2022 |
| Rapport sur les produits sur la plateform | Intégration les produits ACMAD dans la plateforme MyDEWETRA | • intégrer les inventaires et les catalogue des produits identifies dans MyDEWETRA | 08/11/2022 | 10/11/2022 |
|  |  | • formater les produits, importer et faire visualiser en format de MyDEWETRA | 12/11/2022 | 16/11/2022 |
| Rapport sur l'utilisation du site | Rapport présentant les commentaires des parties prenantes/utilisateurs et leur analyse | • installation des outils de suivi | 04/11/2022 | 05/11/2022 |
|  |  | • élaborer les statisques des visiteurs, analyser dans le rapport | 11/11/2022 | 12/11/2022 |
| Rapport sur le geoportail | Concevoir et mettre en place un Géoportail | •état de lieu de l’existant à l’ACMAD puis concevoir l’architecture matérielle et logicielle, faire le choix du prototype | 17/11/2022 | 18/11/2022 |
|  |  | •élaborer du plan de conception, développement, test et opérationnalisation du Géoportail | 18/11/2022 | 23/11/2022 |
|  |  | •mettre en œuvre le plan en collaboration avec d’autres experts | 18/11/2022 | 23/11/2022 |
| Rapports mensuels et de fin |  |  | 24/11/2022 | 26/11/2022 |