CONSULTANCY FINAL REPORT:

CONSULTANCY SERVICES

By

Professor Mansur Bako-MATAZU

Climate Services Applications Expert

ClimSA/GFCS Project

Submitted to:

Dr. Pierre H. KAMSU,

ClimSA Project Senior Thematic Expert

Prepared (Month/Year): 30 August 2024

## CONSULTANCY FINAL REPORT

| Region Covered by activities | Africa |
| --- | --- |
| Institution | ACMAD |
| Department/Service | N/A |
| Project | ClimSA Project |
| Position Title | Climate Services Applications Expert |
| Start Month and Year | 6th June 2024 |
| Expected end month and year | 5th September 2024 |

# General Information

| Lead Partner Organization(s) | African Centre of Meteorological Applications for Development (ACMAD) |
| --- | --- |
| Other Partners Involved | Contracting authority: - African Union Commission (AUC) – Contracting authority. Implementation partners: - European Organization for the Exploitation of Meteorological Satellites (EUMETSAT). - Joint Research Centre (JRC)World Meteorological Organization (WMO). - Copernicus |
| Names and position of Activity Lead (Corresponding author of this report) | Prof. Mansur Bako-MATAZU Climate Services Applications Expert |
| Support Staff contributing or co-authors if applicable | Dr. Andre Kamga FOAMOUHOUE, Dr. Pierre H. Kamsu, Dr. Abiodum Lawal, Mr. Hubert Kabengela, Mr. Leon Guy Razafindrakoto, Mr. Godefroy Nshimirimana, Wendlasida Sandrine Combere |
| Reporting Period (start and end months and years) | 6th June 2022 to 30th August 2024 |
| Date of Report | 30 August 2024 [submitted 5 days before end of contract] |

# Overview of the Consultancy

The African Center of Meteorological Applications for Development (ACMAD) in its capacity as Intra –ACP Climate Services and Related Applications (ClimSA) Program beneficiary has contracted Prof. Mansur Bako-MATAZU as Short-Term Expert in Climate Services Applications under ClimSA/GFCS Project based in Niamey, Niger.  In 2024, ACMAD aims at expanding the Regional Climate Centre for Africa and the Continental Multi Hazards Advisory Centre products and accelerating the operationalization of User Interface Platforms established. Establishing an integrating multidisciplinary systems development team was considered for products development for such decision systems

Under this consultancy services, Prof. MATAZU provides the following services:

- Based on WMO manuals and guides on climate services User Engagement and Interface platform, plan and organize User engagement and Interface platform establishment events.

- Support organization of UIP sessions in conferences, fora, seminars and trainings.

- Document sectoral needs, user services requirements and feedback on services use.

- Review and update web pages and other web-based tools contents used for user engagement in ACMAD/ClimSA selected sectors.

- Organize interactive online activities (i.e., seminars, workshops) to operationalize interactions between people or organizations constituting each UIP.

- Promote one provider and one user focused relationship for specific climate services tailoring and valuation.

- Contribute to capacity building for users of climate information.

- Contribute training material on establishing and operating UIPs.

- Contribute with documented good examples on effective user interface delivering anticipatory action including related benefits for selected sectors.

- Provide support upon request to produce the state of Africa climate and climate services reports with emphasis on the state of UIPs

- Carry out other relevant duties as required.

Matazu provides and or supports the following deliverables:

- Database and updates with contact details of UIP water, agriculture, health and Infrastructure stakeholders

- Online catalogue of products and services collected as requirements for each UIP established and made available online

- 4 UIPs products Web platforms built with opensource tools and interactive wed based survey questionnaire

- Reports on Online webinars or sessions organized to engage stakeholders of each UIP for understanding and use of online information services platforms

- Online feedback forms on each UIP products web platform

- Completed feedback forms and analysis report

- Report on user interaction sessions at the Africa continental Climate Outlook For a and other events

- Reports describing any updates on products and services based on user engagement events

# Project Activities/deliverables planned and related achievements

Activities/Deliverable; Achievements; Constrains/opportunities. - Output 1: Improved Database and updates with contact details of UIP water, agriculture, health and Infrastructure stakeholders:. Activity 1.1: Plan and Organize User Engagement and Interface Platforms using the current UIPs’ database. Held User Engagement Sessions during periodic Briefing and Onset Monitoring Training platforms.; Member Countries were sensitized during periodic forecast briefing and Onset Monitoring training session.; Some Countries and AUC Officials already indicated interest.. Activity1.2: Create an updated database covering the 4 UIPs. The 4 UIPs’ database update using training and RCOPs’ platforms.; Successfully updated the 4 UIPs’ database with new contacts list and details. sgbd.acmad.org:8080/thredds/fileServer/ACMAD/PROJECTS/CLIMSA/CS_UIPs/UIPWaterMailing List.txt sgbd.acmad.org:8080/thredds/fileServer/ACMAD/PROJECTS/CLIMSA/CS_UIPs/NDJAMENA WUIP.txt Water User Interference Platform Water User Interface Platform is committed to strengthening Establish network for knowledge exchanges and better hydrological early warning. (acmad.org) UIP_list of ACMAD users (8).xlsx (live.com); This is progressively being updated leveraging different fora/platforms.. Activity 1.3: Support the organization of UIP sessions in Conferences, seminars & trainings.. Support the organization of Global Flood Partnership Workshop, the Africa Risk Forum Technical Workshop as well as KADI Climate Services Technical Workshop(online).; Successfully supported & participated in the 3 workshops and UIPs’ sessions facilitated. https://view.officeapps.live.com/op/view.aspx?src=http%3A%2F%2Fsgbd.acmad.org%3A8080%2Fthredds%2FfileServer%2FACMAD%2FPROJECTS%2FCLIMSA%2FCS_UIPs%2FACMAD_Presentation_GFD%2520Workshop_Nairobi_24July2024forUIP%2520Water.pptx&wdOrigin=BROWSELINK sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/UIP workshop -Introduction to UIP.pptx.html; Myriad stakeholders sensitized and best practices shared for adoption in the value chain.. Output 2: Online catalogue of products and services collected as requirements for each UIP established.. Activity 2.1 Review the existing catalogs of available products and services.. Sectoral climate risks identified, climate services need per sector enumerated and exhaustively analyzed as captured during the first continental User.; Reviewed the existing catalogs of the available products and services by the project. sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/NCOF_Cameroun_Onset Validation_2024.docx.html; The detailed report provides baseline information on the products/services’ catalogs.. Activity 2.2: Interact with user interfaces platforms to identify needs for uptake in products/services’ generation.. Retrieve and internalize the Needs Assessment Response of Users during the 2024 ACCOF.; Successfully digested the responses and used them to improve products/services. Validation Presentation PRESSAS 2024 Matazu (Verification Mechanism for better CS); None. Participate in series of Briefings and Bi-monthly WHO/ACMAD Coordination meetings; Raised several issues for improvement of the tailored products including redefining the meningitis belt. sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/ACMAD_Meningitis-Clim%5E0Env-Factors_TN_20240711_2.pdf.html; New research window opened with the users: WHO/AFRO.. Participate in Onset Monitoring Engagement with member countries and RCC; Facilitated an Onset Monitoring Validation Mechanism for users. sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/PRESAC User Engagement Concept.docx.html view.officeapps.live.com/op/view.aspx?src=http%3A%2F%2Fsgbd.acmad.org%3A8080%2Fthredds%2FfileServer%2FACMAD%2FPROJECTS%2FCLIMSA%2FCS_UIPs%2FNote_Dinformation_english%2520(1).docx&wdOrigin=BROWSELINK; Action to improve one-stop-shop window information provision to the users.. Output 3: 4 UIPs products Web platforms built with open-source tools and interactive web-based survey questionnaire.. Activity 3.1: Review and update webpages and other web-based tools/contents used for user engagement in collaboration with IT Expert.. Develop online Questionnaires to generate elaborate needs of users to inform co-explored products.; Survey tools being analyzed to refine new products/services. PRESAC-19 Questionnaire ACMAD; Centre’s web site being upgraded to a new version to accommodate this.. Activity 3.2: Organize interactive online workshops/seminars to operationalize interactions between users/organizations constituting each UIP.. Online Training Session on Onset Monitoring Tool for the National Users in Africa.; Assisted in facilitating the training session and the feedback mechanism. sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Presass 2024 UIP.pptx.html; None. Output 4: Reports of Online webinars or sessions organized to engage of each UIP for understanding and use of online information services platforms.. Activity 4.1: Update the thematic products/services catalogs developed based on the capacity building provided for users of climate information. Planned for additional seminars/workshops to build sector-based capacity for improved products/services.; Input into several publications, social media posts.; None. Output 5: Online feedback forms on each UIP products web platform developed. Activity 5.1: Examine existing instruction manuals and procedures for the implementation of climate services at ACMAD.. Instruction manuals and procedures being reviewed; Close consultation with the Senior Thematic Expert. UIP workshop report Agriculture UIP DRR UIP Health UIP Water UIP; None. Activity 5.2: Develop missing instruction and procedure manuals. Ongoing effort to generate the missing gap in the manuals/procedures; Close consultation with the Senior Thematic Expert to achieve this.; None. Output 6: Completed feedback forms and analysis reports. Activity 6.1: Review and update the existing feedback questionnaire instrument material already developed for each UIP. Updated UIPs questionnaires developed; Copies of the updated Questionnaires PRESAC-19 ACMAD. Activity 6.2: Contribute to the development of Visibility Materials for Products & Services. Contribute to development of media/visibility materials on the website and social media handles; Successfully contributed to myriad visibility/media material, products & services published on website & social media handles sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Note_Dinformation_english (1).docx.html; None. Activity 6.3: Support Forums and Events on the benefits for uptake of climate information in the 4 ClimSA focused sectors. Share experience on the socio-economic benefits for uptake of climate information in agriculture, DRR, Health and Water sector; Successfully supported myriad sessions to share experience and needs for adoption of integrating weather information in in the focused ClimSA sectors PRESAC User Engagement Concept.docx (live.com) sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Presass 2024 UIP Validation Presentation.pdf.html; None. Output 7: Report on User Interaction Sessions at the Africa Continental Climate Outlook Forum (ACCOF) and other Events. Activity 7.1: Support and Coordinate to the development of UIP training materials for National Experts. Support update training materials to operationalize the established UIPs; Liaising with the Team Lead to integrate additional inputs into the training materials for UIP sessions; None. Activity 7.2: Support and Coordinate in training for National Experts. Provide support during coordination training for national experts; Developed Concept Notes &presentations for Training Sessions during upcoming NCOF coming up in Cameroun sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/PRESSAC_ 2024_UIP.pptx.html sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/PRESAC User Engagement Concept.docx.html sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Presass 2024 UIP.pdf.html sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Concept Note-NCOF-Cameroon.docx.html; None. Activity 7.3: Participate in training/seminars organized by partners for the use of climate information to achieve sustainable development. Participate in series of trainings/seminar for the use/benefits of climate information to achieve sustainable development; Participated and presented best practices/case studies on the benefits for the use of climate information to achieve sustainable development. sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/CS NiMet Presentation.pptx.html sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/ACMAD_Presentation_GFDWorkshop_Nairobi_24July2024forUIP Water.pptx.html sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/ACMAD_Presentation_ARCMeeting_Accra_July2024.pptx.html. Output 8: Reports describing any updates on products and services on user engagement. Activity 8.1: Participate in review of current bulletins, technical notes, policy making decision support tools on weather and climate and proffer recommendations for improvement. Ongoing effort to achieve this; Ongoing sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Communique Finale_PRESAC-19_Vf.pdf.html; None. Activity 8.2: Contribute documented good examples in any member country/partner on effective use of interface delivering anticipatory sectoral benefits derived in the ClimSA Project. Contribute and share good practices/example on effective use of climate service delivering anticipatory derived; Developed presentations for the upcoming NCOF in Cameroun to share best practices on the benefits of effective use of interface delivering anticipatory actions sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/CSNiMetPresentation.pptx.html; None. Activity 8.3: Participate in specific meetings, consultations for workshops and conferences to update communication channels and contents for more active user engagement to improve the visibility of NMHSs and ACMAD. Support contents and ideas to improve communication strategies/channels; Participated during periodic briefing to enhance Continental and NMHSs’ active user engagement for improved visibility. sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Note_Dinformation_english (1).docx.html; None.

| Extent to which deliverable/outputs are Achieved | Please mark with one box only |
| --- | --- |
| D1: Improved Database and updates with contact details of UIP water, agriculture, health and Infrastructure stakeholders | Ongoing UIP_list of ACMAD users (8).xlsx (live.com) |
| D2: Online catalogue of products and services collected as requirements for each UIP established. | Ongoing Validation Presentation PRESSAS 2024 Matazu (Verification Mechanism for better CS) |
| D3: 4 UIPs products Web platforms built with open-source tools and interactive web-based survey questionnaire. | Ongoing UIP workshop report PRESAC-19 Questionnaire ACMAD |
| D4: Reports of Online webinars or sessions organized to engage each UIP for understanding and use of online information services platforms. | Ongoing |
| D5: Online feedback forms on each UIP products web platform developed. | Ongoing Online feedback Questionnaire ACMAD |
| D6: Completed feedback forms and analysis report | Ongoing UIP user survey PRESAC-19 Questionnaire ACMAD |
| D7: Report on User Interaction Sessions at the Africa Continental Climate Outlook Forum (ACCOF) and other Events. | Yet to Achieve sgbd.acmad.org:8080/thredds/dodsC/ACMAD/PROJECTS/CLIMSA/CS_UIPs/Communique Finale_PRESAC-19_Vf.pdf.html |
| D8: Reports describing any updates on products and services on user engagement. | Yet to Achieve |
| Carry out other relevant duties as required. | Ongoing |

Factors that prevented full achievement of the related tasks

Time factor and also achieving other deliverables depends on the full new website being upgraded currently.

# Risks, issues and mitigation actions

Provide detail on any risks or issues you have encountered in the implementation period. Please include detail on the mitigating actions you are taking in response to this.

| Identified risk or issue | Mitigation action |
| --- | --- |
| None | None |

# Lessons learned and recommendations

Please describe any key lessons learned during the period that you feel could be shared with others. Do you have any recommendations for future initiatives based on these lessons learned?

- Partners of ACMAD to be sensitized on the need for early preparations for a event that the Centre is co-facilitating. - Need to build internal capacity of communication units/expert to ensure roles such as managing and ensuring effective visibility actions from remote event participants are seamlessly executed.

# Additional items for discussion

Please add any further bullet points on key items to discuss.

- ACMAD as the secretariat organization for all the continental sectoral User Interface Platforms for Agriculture, DRR, Health and Water should initiate internation Coordination meeting of the UIP’s focal points to enhance performance monitoring and improved service delivery.

| Signatures |  |
| --- | --- |
| Prof. Mansur Bako-MATAZU Climate Services Applications Expert | Pierre H. KAMSU TAMO, PhD ClimSA Project Senior Thematic Expert |