# ANNEX Ii

## Continental Climate Thematic Action (THEMA) Logical Framework

Note:

1. This logical framework is the result of considerable consolidation efforts done during the Continental Climate THEMA Inception Period. It forms the basis for continuous Monitoring and Evaluation (M&E) during the implementation of the thematic action. Following the careful M&E, indicators and targets will be adjusted as deemed necessary.

2. The description of the Result Area (output) indicators (e.g. R1-IND 1.1) directly refer to the numbering of the corresponding outputs in the Implementation Plan, Chapter 9.

3. If not stated otherwise [e.g. Project Month T3] the time horizon of the SMART (output) indicators is 36 months [T36]. Reference is made to the detailed description of the Work Packages.

4. Any texts in green highlight indicators, sources & means of verification and assumptions related to outputs which are funded by external budget sources. They are nevertheless mentioned in the Implementation Plan logical framework for the sake of completeness.

|  | Intervention Logic | Objectively verifiable indicators of achievement (output indicators) | Sources and means of verification | Assumptions |
| --- | --- | --- | --- | --- |
|  |  | Indicator # | Description | Target |  | Target | Status |  |
| Overall Objective | To increase climate information within the African continent through enhanced capacity of African continental, regional and national institutions by providing new and improved climate services for DRR and enhanced regional collaboration through better access to Earth Observation, communication, strengthened policy frameworks and capacity building. | OO-IND1 | Continental Level: Policy and decision makers at continental level regularly receive services (reports, bulletins, policy briefs) provided by the Continental Climate THEMA and use them for "informed decisions". | 3 | Report on Continental Climate THEMA services provision on continental level, including user feedback | 3 | 0 |  |
|  |  | OO-IND2 | Regional level: Policy and decision makers at regional level and end-users in a given region mandated to be enclosed by the respective RIC regularly receive services (reports, bulletins, policy briefs) provided by the Continental Climate THEMA and use them for "informed decisions". | 3 | Report on Continental Climate THEMA services provision on regional and end-user level, including user feedback | 3 | 0 |  |
|  |  |  |  | 3 | Report on Continental Climate THEMA services being regularly integrated in RIC’s services, including user feedback | 3 | 0 |  |
| Purpose | Enhanced capacities to manage climate related disasters through improved climate services, information and training. | P-IND 1 | AUC and RECs have clearly defined mandates for climate related disasters management and en-vironmental monitoring. | Done | Continental Climate THEMA Final Report | Done | Not done | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. RECs act as an efficient interlocutor between the international and continental community and their national member states. The MESA Programme PSC and the Continental Steering Committee (CSC) of the Continental Climate THEMA provide ultimate guidance. Decision makers at all levels recognize the value of MESA Continental Climate THEMA services, are responsive to the information, and are willing to invest in order to sustain them. |
|  |  | P-IND 2 | Monitoring and decisions on environmental policies are routinely taken, and include EO based Continental Climate THEMA services on continental, regional and end-user level. | Done | Review Report of Continental (AUC), regional (RECs), and national (AU member countries) reports. | Done | Not done |  |
|  |  | P-IND 3 | Key policy, planning instruments and mechanisms for climate related disasters management and environmental monitoring have been formalized within the African Union Commission. | Done | Continental Climate THEMA Final Report | Done | Not done |  |
|  |  |  |  | 3x | Formalization mentioned in proceedings of international conferences and symposia | 3x | 0 |  |
|  |  |  |  | 3 | Requests for Continental Climate THEMA services | 3 | 0 |  |
| Result Area 1 | Access to existing EO, field and ancillary climate data improved and sustained by maintenance of AMESD Station, installation of MESA Stations and by dissemination of essential datasets via FPs and Universities | R1-IND 1.1 | Maintained AMESD Station (ACMAD) [T3] and three MESA Stations (ACMAD, UoD, UoN) [T 12] operational | 100% | Report on operational status | 100% | 25% | EU Earth Observation (EO) technology is operational and EO policies assure long-term services provision. Support by TAT, Addis Ababa, JRC and EUMETSAT is provided, giving priority provision of MESA stations to ACMAD, UoD, UoN (not participating in AMESD). |
|  |  |  |  | 100% | Annual Report on operational status | 100% | 25% |  |
|  |  | R1-IND 1.2 | Data Centre, Rolling Archive / Backup System / Mirror Site and Website operational [T12] | Signed | Agreement documents with data providers | Signed | Not signed | Support by TAT, Addis Ababa, JRC and EUMETSAT is provided. MESA Supply Tender Lot #2 indeed facilitates Continental Information Management for ACMAD and Continental Climate THEMA partners. |
|  |  |  |  | 100% | Annual Report on operational status of GIS capability and Data Centre | 100% | O% |  |
|  |  |  |  | 90% | Annual Report on operational data acquisition status | 90% | 0% |  |
|  |  |  |  | 90% | Annual Report on operational data distribution status | 90% | 0% |  |
|  |  |  |  | 100% | Annual Report on operational status rolling archive / backup system / mirror site | 100% | 0% |  |
|  |  |  |  | 100% | Annual Report on operational status of website | 100% | 0% |  |
|  |  |  |  | 6,000 users p.a. | Annual Report on user access to website | 6,000 users p.a. | 0% |  |
| Result Area 2 | Operational climate services for DRR improved to better manage environmental resources, thus contributing to better decision-making and planning at continental and regional levels. | R2 IND 2.1 | Definitions and Specifica-tions for two Continental Climate THEMA services (CCTSs) prepared: 1. Climate Change Assess-ment Service 2. Drought Service and Seasonal Climate Fore-cast | 2 CCTSs | Working Plan of activities and tasks with milestones | 2 CCTSs | 0 | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. MESA Non Key Expert provides support for drafting the Continental Climate THEMA Service Development Plan |
|  |  |  |  |  | Needs & Assessment Report |  |  |  |
|  |  |  |  |  | Technical Specifications of Climate Services |  |  |  |
|  |  |  |  |  | Service Development Plan |  |  |  |
|  |  | R2 IND 2.2 | Development for two CCTSs prepared | 2 CCTSs | Continental Climate THEMA Service Catalogue | 2 CCTSs | 0 | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. |
|  |  | R2 IND 2.3 | Integration and Validation for two CCTSs prepared | 2 CCTSs | Integration and Validation Report | 2 CCTSs | 0 | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. |
|  |  |  |  |  | Climate Services beta version [T12] |  |  |  |
|  |  | R2 IND 2.4 | Operation for two CCTSs prepared | 2 CCTSs | Climate Services operational | 2 CCTSs | 0 | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. |
|  |  |  |  |  | Report on Milestones and Service Releases |  |  |  |
|  |  | R2 IND 2.5 | User Support and Feedback for two CCTSs organized | 2 CCTSs | User Support Report | 2 CCTSs | 0 | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. |
|  |  |  |  |  | Continental Reports accompanied by Policy Briefs |  |  |  |
|  |  |  |  |  | User Fora Feedback Report |  |  |  |
| Result Area 3 | Collaboration between regions in Africa strengthened through enhanced climate thematic action cooperation of ACMAD with RICs and Universities. | R3 IND 3.1 | Collaboration between regions in Africa improved and ensured through enhanced thematic cooperation of ACMAD with RICs | 5 MoUs | Signed MoU between ACMAD, AGRHYMET, ICPAD BDSM, UoD and UoN | 5 MoUs | 0 | Continental Climate THEMA partners are committed to co-operation as agreed upon in the Grant Proposal. |
|  |  |  |  | 4 CSC 4 CWC | Minutes of Meeting of CSC and CWC | 4 CSC 4 CWC | 0 CSC 0 CWC |  |
|  |  |  |  | 6 | Joint visibility and (Social) Media events | 6 | 0 |  |
|  |  | R3 IND 3.2 | MESA Cross-Fertilization & Continentalisation supported | 6 CEBs | MESA Continental Environmental Bulletins (CEBs) | 6 CEBs | 1 CEB | Since support to the MESA Continental Environmental Bulletins by ACMAD is not budgeted in the Continental Climate THEMA Grant, additional resources are made available by MESA TAT. |
|  |  |  |  | 2 | Reports on collaboration with European institutions | 2 | 0 | European institutions are interested in collaborations. |
| Result Area 4 | Political and policy development frameworks strengthened across the continent to ensure an active and sustainable participation of African stakeholders in initiatives concerning EO for environment and security. | R4 IND 4.1 | User-friendly and tailored climate and climate change information disseminated to policy makers | 3 | Incorporation of the Continental Climate Services in the reporting cycle of mandated stakeholders | 3 | 0 | Mandated stakeholders provide feedback via operational feedback mechanisms. |
|  |  |  |  | 500 actors | Actors / networks data base | 500 actors | 0 | Policy makers consider Continental Climate THEMA services being relevant. |
|  |  |  |  | 4 Cont / 6 Reg | Policy Dialogue Open Day (Continental / Regional) | 4 Cont / 6 Reg | 0 | Policy makers consider Continental Climate THEMA services being relevant. |
|  |  |  |  | 4 Cont / 6 Reg | Visibility events promoting the use of EO (Continental / Regional) | 4 Cont / 6 Reg | 0 | Policy makers consider Continental Climate THEMA services being relevant. |
|  |  | R4 IND 4.2 | Climate and climate change services advocated and translated into DRM services to facilitate disaster preparedness | 1 | New tailored Continental Climate THEMA service | 1 | 0 | Policy makers and DRM consider Continental Climate THEMA services being relevant. |
|  |  |  |  | 12 | Policy Briefs | 12 | 1 |  |
|  |  |  |  | 3 | Technical Reports | 3 | 0 |  |
|  |  |  |  | 3 | MoM Roundtables | 3 | 0 |  |
|  |  |  |  | 3 | Reports on Symposia & Fora | 3 | 0 |  |
|  |  |  |  | 10 | Policy Dialogue Open Days | 10 | 0 |  |
|  |  |  |  | 10 | Reports on Service User Feedbacks | 10 | 0 |  |
|  |  | R4 IND 4.3 | Climate and climate change services advocated by the Climate THEMA Continental Steering Committee | 3 | Continental Climate THEMA Services Brands | 3 | 0 | Climate THEMA Continental Steering Committee strongly committed to its guidance role. |
|  |  |  |  | 4 | Targeted Policy Briefs | 4 | 0 |  |
|  |  |  |  | 4 | Tailored Continental Climate THEMA Services Bulletins accompanied by Policy Briefs | 4 | 0 | Continental Climate THEMA CSC requests specific and tailored Continental Climate THEMA Services and Policy Briefs. |
| Result Area 5 | Climate services capacity of major stakeholders in Africa enhanced and delivered by continental and regional training and workshop events in cooperation with RICs and Universities. | R5 IND 5.1 | Continental Climate THEMA Training Package developed and delivered | Done | Continental Climate THEMA Training Package | Done | Not done | Continental Climate THEMA partner Universities have operational AMESD / MESA Stations on hand. |
|  |  | R5 IND 5.2 | Pool of Trained-Trainers (TT), being multipliers and ambassadors alike for Continental Climate Services, available by means of Continental Climate THEMA Training and Workshop events at Continental Level | 20 TT | Pool of Trained-Trainers (TT) for Continental Climate THEMA Services at Continental Level | 20 TT | 0 TT | At least 50% of the Trained-Trainers (TT) fulfils the demanding requirements as outlined in the Focal Points (FPs) ToR. |
|  |  | R5 IND 5.3 | Pool of additional Trained-Trainers (TT), being multipliers and ambassadors alike for Continental Climate Services with reach-outs to end-users in a given region trained and available | 22 AGR HY MET 16 ICPAC 18 BDMS | Pool of additional Trained-Trainers (TT) for Continental Climate THEMA Services with reach-outs to end-users in a given region | 22 AGR HY MET 16 ICPAC 18 BDMS | 0 |  |
|  |  | R5 IND 5.4 | Continental Climate THEMA Distance Education Package compiled and delivered, | Done | Continental Climate THEMA Distance Education Package | Done | Not done | Promotion of Distance Education motivates at least 20 new distance learners to become Continental Climate THEMA Focal Points (FPs). |
|  |  | R5 IND 5.5 | Pool of additionally qualified Focal Points (FPs) trained | 20 | Pool of additionally qualified Focal Points (FPs) by means of On-The-Job-Training | 20 | 0 | On-The-Job-Training is requested by Focal Points (FPs). |
|  |  | R5 IND 5.6 | Pool of skilled EO and Continental Climate THEMA Junior Experts in Africa on the long-term trained by means of support to Universities on Curriculum Development with stand alone training material and R&D activities | Done | Adapted Continental Climate THEMA training package for University Curricula available | Done | Not done | The Board of Directors of the Universities supports the Continental Climate THEMA Curriculum Development and R&D initiatives. |
|  |  |  |  | 4 | Relevant students projects reports | 4 | 0 | Universities supervisors motivate students for Continental Climate THEMA services. |